**Asha Mumbai Center Covid19 disaster relief 2020 26/04/2020**

Date 04/05/2019

|  |  |  |
| --- | --- | --- |
|  | **Project Contact Information** | **Asha Contact** |
| **Name** | Rekha Bose | Dr. SmitaPuniyani |
| **Contact Address** | 2 E flat no 602  Powai Vihar complex  Powai Mumbai 400076 | Asha Mumbai Centre. Ground Floor, PowainookBldg, oppTirandaz Municipal school. Opp. IIT Main gate,Powai Mumbai 400076. |
| **Phone** | 9821129946 | 9869365092 |
| **E-mail ID** | rekha.rb@gmail.com | [Smita.puniyani@gmail.com](mailto:Smita.puniyani@gmail.com) |

Please see for updates of progress of project.

**Proposed work:ASHA MUMBAI CENETR**

**This proposal is for the Covid19 disaster relief work.**

**Objective :**

**To support the poor and marginalized section with food and Ration supply.**

**The plan is for next two months**

**Action Plan**

1. **To distribute dry ration to the families of Asha Students and others in similar conditions therby covering most of the communities around Powai**
2. **To try and support the migrant workers and their families with cooked food or Dry rations**
3. **Post lockdown supporting people with medical needs**
4. **To plan the digital classes for Asha Students**
5. **To carry out correct information dissemination through posters ,pamphlets etc to create the awareness .**

**Financial Details:**

The proposed expenditure is as follows:

|  |  |  |  |
| --- | --- | --- | --- |
| **No.** | **Details** | **quantity** | **Amount** |
| **1** | Dry rations | 500x300 families | 450000/-  7.5 kg aata+ 2kg pulses +2 litres oil+2kg onions and potatoes. Rice we expect sooner or later govt supply will start for the non ration card holders as well |
| **2** | Transportation of the  grains from shops to center | 300 per day x 60 days | 18000/-includes transport for all purposes. |
| **3** | Budget allocation for medical help | As per the demand | 100000/- |
| **4** | Plan for digital classes | 2 Teachers 5000x2 | 20000/- |
| **5** | Posters creation and priting ,pasting | 3000 pamphlets | 10000/- |
| **6** | Personnel for cooking | 10000/- PM | 20000/- |
| **7** | Distribution materials | 3000/- (approx) | 3000/- |
| **8** |  |  |  |
| **10** | Total |  | 621000/- |

( in words ,six lac twenty one thousands only)

Asha Mumbai Chapter coordinator

DrSmitaPuniyani