## Sheet1
Dated 20th Jan 2003
Accounts for money sent to Tea Trust as per accounts given by Sri Arputham and vouchers verified by Sri Narasimhan
First instalment to TEA trust: $2000.00 (Rs. 90,000)
Second : $1277.78 (Rs. 57,000)
Facilitator salary + TA : $ 666.67 (Rs. 30,000)
Total : $3944.45 (Rs.177,000)
Total fund received on 16/08/03= Rs 91,121=$2000
School | Head of expense | Allotment for the year from the funds receivedin th first instalment | Details of expenses June 03-Oct 03 in Rs | Projected till Jan2004 | Balance in hand in that head | Remarks
Kolathancheri | Teacher salary @ Rs1000 per month per teacher | 12000 | 5000 | 3000 | 4000
Venbakam | Teacher salary @ Rs1000 per month per teacher | 6000 | 5000 | 3000 | -2000
Both schools | Village meeting | 1000 | 500 |  |  | Can be called anytime in Jan-feb
Kolathancheri | Plates and vessels | 1000 | 0 | Advised to go ahead with the purchases | 0
Venbakam | Plates and vessels | 1000 | 0 | Advised to go ahead with the purchases | 0
Kolathancheri | Worksheet materials | 1000 | 0 | Materials were given from Rightstart teacher training for flash cards | 1000
Venbakam | Worksheet materials | 1000 | 0 | Materials were given from Rightstart teacher training for flash cards | 1000
Kolathancheri | Flooring | 30000 | 16269 | 0 | 13731 | Narasimhan reports- the work is well done
Kolathancheri | Toilet | 10000 | 0 | The SSA may provide money for a toilet.The amount can be saved or added to supplement the SSA funding | 10000 | Will be required anytime
Both schools | Learner's achievement tests | 1500 | 0 | Was to be conducted in Dec- Jan2003 Will be handled in Feb2004 | 1500 | Required in end Jan
Both schools | Blackboards and other infrastructure | 5000 | 2795 | 0 | 2205
Arputham | Cordinators salary | 18000 | 15000 | 9000 | -6000
|  | 87500 | 44564 | 15000 | 27936
If II instalment is sent now it will take a couple of months for the money to be realised.
As regards the facilitator from Chennai- The original person we had in mind did not join as we could not get her at Rs2000
alloted by MIT for that purpose. Project Rightstart training came in very useful and save some money as well.
We plan to start the evaluations with a team of teachers from my school as we are doing the same with the corporation school
nearby. Sathyapriya and Thangadurai are being trained for the work in conjunction with these teachers. Now we will be able to
utilise the funds for the facilitators effectively.
So I request that Rs15,000 of Rs30,000 set aside for the facilitaors be sent for use till May2003
Suggestions
Some of the money saved from various heads must be utilised in buying teaching learning matearials as we have provided
in the other schools we are working with. These would include, library books, atlases, colors, geometrical instruments
and containers to store them, classroom cupboards….
These things improve the quality of the teaching learnig processes. We have these experiences improving quality in Olcott school
Rishiyur school, Balwadis in Chennai and Rishiyur