- Introduction.

- Program Goal

- Specific objectives

- PART- 1

- Outcome in terms of Quantitative changes (After 2nd quarter progress):

- Pre Primary Education Centre

- Primary Education Centre

- Right to Development.

- Right to Protection.

- Right to Survival.

- Holiday Camp

- Network Activities:

- Major Achievements:

- Other Activities.

  - In- house Training / Meeting / Workshop

  - Outside Training / Meeting / Workshop

- CASE STUDY: -

- PART- 2: IMPACT INDICATORS

- INTRODUCTION: - Education is the process of receiving or giving systematic instruction, especially at a school or institution. This is an activity that imparts knowledge. Like previous quarter in 2nd Quarter the main goal of the program was education through triangular relationship among – the Child, the Teacher and the Community. Through the proper knowledge of correct social behaviour, awareness building can be done among community. Awareness of the parent about the importance of education of children is very much necessary for any sustainable education programme. So, in any sustainable educational program, the participation of community and teachers is must.

- PROGRAMME GOAL:

- Specific objectives:-

  - Ensure Children Rights for their Socio-education- cultural Development.

  - A Child of the age group of (0—18) yrs should be considered as a child.

  - The basic Health Programme should cover all Children.

  - An Appropriate and systematic Educational Network should built in entire district along with a sustainable Coordination with the rural people and all other parts of the society.

  - Campaign on Common School System (CSS) in every pocket of working areas.

- About Pre- Primary Education Centre.

- About Primary School

- About Developmental Rights

- About Survival Rights

- About Protection Rights

- Holiday Camp.

1.BAGMUNDI: - 09 children have been mainstreamed into Primary School from this centre. More interests are seen among the parents. Other than our 19 students some quite elder children came to the school to study.

2. GHORABANDHA:- 38 children have been mainstreamed into Primary School from this centre. Parents are showing more interest. They often ask the teachers to fill up the form of having birth certificate.

3. SINDRI: - 16 children have been mainstreamed into Primary School. Parent always attends the parent –meeting. One Heath Camp for Women was organized on 07.09.2003.

4. RERENGTARN: - 20 children have been mainstreamed into Primary School from this centre. Parents are more active in this centre.

5. BARUAJARA:  On August 2003 the student strength of this school was 29. In September 28 children were mainstreamed into Govt. Primary School. So, as the total no of the students came down to 1, it was decided after discussion with community and Mandra Lions Club to start a new centre at JHILINGTARN, which is 1.5 km from Baruajara and now at Jhilingtarn the total number of students are 26. (B-10, G- 16).

6. BURDA:  05 children have been mainstreamed into Primary School from this centre.

7. LAHARIA: 24 children were mainstreamed in to Govt Primary School. Lack of involvement of parent is also seen among parents.

8. BONGADA: - 14 children have been mainstreamed into Primary School from this centre. Centre is running well. Due to some illness of the children percentage of attendance was low.

9. AYODHYA: - As entire children (27) have been mainstreamed, the centre is now in pause situation. The main work is now to mainstreamed the other children who are either dropped out or not going to school.

10. BELA: As one parents established in other village, the number of children reduced from 22 to 21. Mainly most of the students belongs to the ‘SABAR’ community, but recently other than Sabar children started to come in the centre.

11. SIRGI: - Community is showing more interest on education of their children. Community included the Teacher of the Pre –Primary school into their Village Education Committee. (VEC).

| Sl. No | Name of the Centre | Students | Average Attend. (In %) / Month | Average Working Days (%) | Animators (Teachers) | Grade |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Boy | Girl | Total | Boy | Girl |  | Trained | Un-trained |  |
| 1 | BAGHMUNDIH | 09 | 10 | 19 | 80 | 85 | 100 | 2 | -- | A |
| 2 | GHORABANDHA | 26 | 30 | 56 | 37 | 35 | 100 | 2 | -- | B |
| 3 | SINDHRI | 28 | 22 | 50 | 68 | 58 | 100 | 2 | -- | A |
| 4 | RERENGTANR | 17 | 16 | 33 | 67 | 67 | 100 | 2 | -- | B |
| 5 | BARUAJARA | 10 | 19 | 29 | 45 | 43 | 98 | 2 | -- | B |
| 6 | BURDA | 15 | 21 | 36 | 67 | 75 | 97 | 2 | -- | B |
| 7 | LAHARIA | 22 | 12 | 34 | 36 | 73 | 100 | 1 | 1 | B |
| 8. | BONGADA | 30 | 07 | 37 | 62 | 77 | 90 | 2 | - | A |
| 9. | SIRGI | 11 | 08 | 19 | 67 | 80 | 96 | -- | 1 | B |
| 10. | BELA | 13 | 09 | 22 | 58 | 58 | 95 | -- | 1 | B |
|  | Total | 181 | 154 | 335 |  |  |  |  |  |  |

This Primary School is daily in progress. Parents are showing interest. Half yearly examination was also done.

| Sl. No | Name of the Centre | Students | Average Attend. (In %) / Month | Average Working Days (%) | Animators (Teachers) | Grade |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Boy | Girl | Total | Boy | Girl |  | Trained | Un-trained |  |
| 1 | Aloke Kendra Primary School, Bagmundi. | 19 | 09 | 28 | 92 | 95 | 100 | -- | 3 | B |

One Training for Animator (Teacher) by VERS is very much necessary .At present those Animators are working, are trained by MLC.

OUTCOMES IN TERMS OF QUANTITATIVE CHANGES AFTER 2ND QUARTER (JULY—SEP’03)

### DEVELOPMENT RIGHTS

| Sub | Parameter | Yearly Tar get | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieve | T | A | T | A | T | A |  |  |
| EDUCAT I ON | 1. No of Pre-Primary center run by the Orgn. | 11 |  | 11 |  | 11 | 11 |  |  |  | It’s an ongoing process. |  |
|  | 2. No of Non formal centers for school drop outs | NA |  | -- |  |  |  |  |  |  |  |  |
|  | 3. No of children attended by the Non- Formal centres. | NA |  | -- |  |  |  |  |  |  |  |  |
|  | 4. No of children covered under Pre –Primary. | 550 |  | 433 |  | 335 | 350 |  |  |  | Met with parents of the children. |  |
|  | 5. No of children from Pre- Primary center admitted to Primary School | 177 |  | 87 |  | 177 |  |  |  |  | According to Govt. Primary School admission session. | Some children can’t to continue due to poverty. |
|  | 6. No of children (5- 18 yrs) going to formal school. | 5269 |  |  |  | 3440 |  |  |  |  |  | Some children drop out from the school. |
|  | 7. No of village with 100% enrollment | 2 | -- | -- |  | -- | 01 |  |  |  | Activities ongoing. | Lack of involvement of community. |
|  | 8. No of Govt. Primary schools interface initiated. | 199 |  | 30 |  | 29 | 33 |  |  |  | Met & discussion with the Teachers. | Non-availability of teachers. |
|  | 9. No of Govt. Primary School Activated. | 14 |  | 02 |  | 02 | 02 |  |  |  | Rerengtarn & Ghorabandha | Lack of interest of teachers |
|  | 10. No of local education committee (LEC). (For Pre-Primary) formed. | 11 |  |  |  | 09 | 02 |  |  |  | Meeting with the LEC. | Lack of awareness of the necessity of LEC. |

DEVELOPMENT RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan. | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieved | T | A | T | A | T | A |  |  |
| EDUCAT I ON | 11. No of local education committee activated. | 09 |  |  |  | 05 | 02 |  |  |  | Capacity Building through empowerment. Meeting & discussion. | Villagers have no so time during the cultivation period. |
|  | 12. No of Panchayat initiated. | 77 |  | 09 |  | 13 | 33 |  |  |  | Discussion. | Have |
|  | 13. No of Panchayat activated in education issues. | 04 |  |  |  | 01 | 01 |  |  |  | Bagmundi | Lack of capacity building of villagers. |
|  | 14. No of village education committee interface initiated. | 66 |  |  |  | 23 | 22 |  |  |  | Meet and discussion | Lack of knowledge on the importance of VEC. |
|  | 15. No of village education committee activated. | 05 |  |  |  | 02 | 02 |  |  |  | Rerengtarn, Bagmundi | Lack of capacity building of villagers. |
|  | 16. House hold visit | 5400 |  | 959 |  | 981 | 1000 |  |  |  | Visit house holds | Non-availability of householder. |
| NETWORK | 17. No of local organization/ Club activated through network | 15 |  |  |  | 03 | 04 |  |  |  | Rerengtarn, Bagmundi, Ghorabandha. Met & discussion. | Lack of capacity building of club members. |
|  | 18. Coordination with orgn. / Club. | 88 |  | 02 |  | 08 | 10 |  |  |  | Met with club members. | Non-availability of club members. |
|  | 19. Block Meeting | 01 |  |  |  |  | 01 |  |  |  | Would be done on 14.11.03 |  |
|  | 20. Rural Rally | 11 |  |  |  |  | 11 |  |  |  | On 14.09.03 |  |
|  | 21.Campaigning with Poster, walling, hat prachar etc. | 11 |  |  |  |  | 11 |  |  |  | On 14.09.03 |  |
|  | 22.Visit with the State Organization |  |  |  |  |  |  |  |  |  |  |  |
|  | 23. State Convention | 01 |  |  |  |  | 01 |  |  |  | On 3rd Qrt |  |
|  | 24. National Convention | 01 |  |  |  |  | 01 |  |  |  | On 16th to 18th Oct.’03 |  |

#### SURVIVAL RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieve | T | A | T | A | T | A |  |  |
| HEALTH AWARENESS | 1. No of children have birth registration certificate (0-14 yrs) | 175 |  | 32 |  | 02 | 15 |  |  |  | Communicating with Panchayat, guardians. | It takes time to efidevit. |
|  | 2. No of children attended by health check up clinics (0-14yrs) | 100% |  | 307 |  | 127 | 180 |  |  |  | Communicating with the health centre. | Lack of knowledge about the importance of check up |
|  | 3. No of children (0-5yrs) fully immunized. | 100% |  |  |  | 24 | 24 |  |  |  | Communicate with HC |  |
|  | 4. No of pregnant mother covered under health care. | 100% |  | 96 |  | 31 | 96 |  |  |  | Communicate with HC | Careless about health care. |
|  | 5. No of mother covered under immunization. | 100% |  | 84 |  | 31 | 84 |  |  |  | Communicate with HC |  |
|  | 6. No of eligible couple practices family planning measures. | 100% |  | 135 |  | 142 | 142 |  |  |  | Communicate with HC |  |
|  | 7. No of Panchayat interface initiated. | 33 |  | 09 |  | 16 | 18 |  |  |  | Meet and discussion | Due to new formation of commt. |
|  | 8. No of Panchayat active in health issues. | 04 |  | -- |  | -- | 02 |  |  |  |  |  |
|  | 9. No of Mahila Samities active in health issues. |  |  |  |  |  |  |  |  |  |  |  |
|  | 10. No. Of health center interface initiated. | 11 |  |  |  | 11 | 11 |  |  |  | Regularly visit |  |
|  | 11. No of health center active. | 04 |  |  |  | -- | 01 |  |  |  | Visit regularly | Lack of time of HW |
|  | 12. Communicate with health worker (HW) | 170 |  | 33 |  | 34 | 35 |  |  |  | Met with HW. | Non-availability of HW. |
|  | 13. No of Health meeting | 44 |  | -- |  | 04 | 10 |  |  |  | Met & discussion. | Lack of time of HW |
|  | 14. Meeting with health committee. | 33 |  | -- |  | -- | 11 |  |  |  | Process is ongoing | Lack of time of HC |
|  | 15. No of local orgn. Activated through network. | 11 |  | -- |  | -- | 02 |  |  |  | Process is ongoing | Lethargy of the local organization. |

#### PROTECTION RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieved | T | A | T | A | T | A |  |  |
|  | 1. No of child labour (5-18yrs) |  |  |  |  |  |  |  |  |  |  |  |
|  | 2. No. of village declared child labour free (upto 14 yrs) | 02 |  | -- |  | -- | 01 |  |  |  | Activities ongoing |  |
|  | 3. No of differently abled children with identity card. |  |  |  |  |  |  |  |  |  |  |  |
|  | 4. No of Self Help Group formed. |  |  |  |  |  |  |  |  |  |  |  |
|  | 5. No of Panchayat interface initiated. | 01 |  | -- |  | -- |  |  |  |  | Activities ongoing |  |
|  | 6. No of Panchayat activated in protection issues. |  |  |  |  |  |  |  |  |  |  |  |
|  | 7. No of local orgn. Activated through network. | 04 |  |  |  | -- | 01 |  |  |  | Process ongoing. |  |

Holiday camp was started on June 2003 with 14 Govt. Primary School of Bagmundi circle II with an objective to reduce the drop out children of class III & IV from school. These camps are showing quite positive impact. As a result of these camps a positive attitude are seen among the teachers. They are taking responsibility and that why the interest of the children are increasing day by day. From starting it was decided to organize Holiday camp and   Follow up in alternative months. So, in 2nd Quarter one Holiday Camp on August and two Follow up camps on July and September have been organized respectively.

But, it was observed that during the Follow up camp on working days, teachers were facing some problems of tackling the entire students of the school. (In holiday camp only student of class III & IV attend the camp).

NETWORK ACTIVITIES

NETWORK ACTIVITIES ON 2ND QUARTER (JULY – SEP 2003)

BY MANDRA LIONS CLUB, BAGMUNDI, PURULIA.

| Sl No. | Date | Venue | Programme/Issue | Discussion | Organized by | Participants | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 06.07.2003 | Rerengtarn | What is WBEN | Discussion with the club member about WBEN | Mandra Lions Club. | 15 |  |
| 2. | 07.07.2003 | Neheu Yuva Kendra, Purulia. | VEC. CSS, WBEN | Discussion with Mr R.S.Naskar of NYK, Purulia. |  |  |  |
| 3. | 13.07.2003 | Bagmundi | On SSK | About Sishu Sikshs Kendra. | Mandra Lions Club. | 19 |  |
| 4. | 20.07.2003 21.07.2003 | Kolkata | VEC, SSK, | Details discussion. |  |  |  |
| 5. | 13.08.2003 | Bagmundi High School, Purulia | Importance of CSS (Common School System) in India. | Discussion on CSS and the importance of CSS in present situation. The impact of LPG (Liberization, Privatization and Globalization) in near future. The impact of Sarba Siksha Abhizan(SSA) and the importance of Sishu Siksha Kendra (SSK). | Deptt. Of Primary Education, Govt of WB, | 312 (Teachers & members of 132 schools) | All participants appreciate the importance of CSS. |
| 6. | 15.08.2003 | Bagmundi, Purulia | About WBEN & CSS. | Discuss about WBEN and the importance of understanding the DPEP. The necessary of CSS in education policy. The harmful impact of LPG on education system. | Mandra Lions Club, Bagmundi, Purulia. | 31 | Members want to meet again to discuss |
| 7. | 16.08.2003 | Mohukodor village, Jhalda II | Importance of CSS in present situation. | What is CSS? What is its importance? | Mandra Lions Club, Bagmundi, | 22 | Rural people want CSS as they can’t cope up with LPG. |
| 8. | 18.08.2003 | Jhalda II Block | Meeting on CSS | Discussion on INHP. Associated with INHP the importance of CSS was also discussed. | Mandra Lions Club, Bagmundi, | 23 |  |
| 9. | 24.08.2003 | Rerengtar, Bagmundi | Role of VEC on CSS | Role of VEC. The actual activities of VEC. Importance of CSS. And the role of VEC on CSS. | Mandra Lions Club, Bagmundi, | 15 | Need Capacity Building of VEC |

NETWORK ACTIVITIES ON 2ND QUARTER (JULY – SEP 2003)

BY MANDRA LIONS CLUB, BAGMUNDI, PURULIA.

| Sl No. | Date | Venue | Programme/Issue | Discussion | Organized by | Participants | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 10. | 04.09.2003 | Ghorabandha, Bagmundi | Role of WBEN in CSS. | What is WBEN? What is CSS? Importance of CSS. Role of WBEN in CSS. | Mandra Lions Club, Bagmundi, | 33 |  |
| 11. | 05.09.2003 | Laharia, Bagmundi | Necessary of CSS. | Details of CSS. Impact of LPG on rural life. Impact of Privatization on Rural Education System. | Mandra Lions Club, Bagmundi, | 58 | Due to Poverty Rural people do not want Privatization |
| 12. | 07.09.2003 | Bagmundi High School, Purulia | Block Forum Formation on CSS | Discuss about CSS and the importance of CSS on our present India. Form a Block Forum on CSS. Discussed on LPG and its impact on future. | Mandra Lions Club, Bagmundi, | 31 | Agreed to form a network to spread the idea of CSS. |
| 13 | 08.09.2003 | Bagmundi | Meeting on CSS | What is CSS? What is its importance? | Mandra Lions Club, Bagmundi, | 22 | Rural people have more interest on CSS rather than urban people. |
| 14. | 08.09.2003 | Jhargram | Perspective Building Workshop on CSS | Role of WBEN in CSS. Feasibility of CSS in India. Role of Teachers in CSS. Impact of LPG in CSS. Role of Govt in CSS. | WBEN, Paschim Midnapore & Jana Siksha Prasar Samity, Jhargram | 6 from MLC | Impact of Privatization will hinder the CSS. |
| 15. | 11.09.2003 12.09.2003 | Baruipur | CSS | Details on CSS |  |  |  |

MAJOR ACTIVITIES

In this 2nd Quarter one Base Line Survey has been completed for the new intervened Jhalda II Block. The new 6 intervened villages are as follows;-

1. Chatambari.	2. Begunkodar.	3. Supurdih-Brindabanpur 4. Murguma		5. Mamudih		6.Laxipur

The Base line survey of these 6 villages has been completed but the compilation of the data are on process. It would be completed very soon. Only some importance data are given below.

BASE LINE SURVEY OF JHALDA II BLOCK ( 6 VILLAGES)

| Sl no. | Survey on | Chatambari Village | Begunkodar Village | Supurdih –Brindabanpur | Murguma | Mamudih | Laxipur |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. | House holds | 228 | 774 | 116 | 352 | 94 | 60 |
| 2. | Population | 1260 | 4631 | 252 | 2339 | 507 | 282 |
| 3. | (0 – 5 yrs) Boys | 83 | 351 | 20 | 201 | 43 | 19 |
| 4. | (0 – 5 yrs) Girls | 74 | 309 | 23 | 188 | 38 | 22 |
| 5. | School going (0 – 5 yrs) Boys | 18 | 193 | 04 | 127 | 06 | 09 |
| 6. | School going (0 – 5 yrs) Girls | 27 | 178 | 04 | 98 | 05 | 08 |

OTHER ACTIVITIES

###### IN-HOUSE TRAINING / WORKSHOP / MEETING

| Sl. No | PROGRAMME | VENUE | DATE / DURATION | PARTICIPANTS | RESOURCE GROUP |
| --- | --- | --- | --- | --- | --- |
| 1 | Planning & Discussion | MLC Meeting Hall | 04.07.2003 | Ext-worker-14, Sup-1, Motivator-1 | MLC Sup, Motiv |
| 2 | Staff meeting | MLC Meeting Hall | 23.07.2003 | PC,Moti-2, Supv-2,Acc-2 | MLC-PHolder |
| 3 | Meeting on CSS & LPG | Bagmundi H School | 15.08.2003 | Project Holder, Motivator | PH |
| 4 | Monthly Teachers meeting | MLC Meeting Hall | 2 days | Ext- worker-19, Motiv-1, Supv-2, PH | PH |
| 5 | Mental Health & Pedagogy | MLC Meeting Hall | 20.8.2003 | Ext- worker –19, - | Edu Sup |
| 6 | Work Shop on CSS, SSK, MSK | MLC Meeting Hall | 22.08.2003 | Ext- w- 18, Sup-2, CO, | PH |
| 7. | Meeting on Block Forum Formation (CSS) | Bagmundi HS School, | 07.09.2003 | Member-31. | MLC- PH |
| 8. | Village meeting | Begunkodor (Jhalda) | 16.09.2003 | Villagers-31 | CRY & MLC |
| 9. | Village Meeting | Rerengtarn | 16.09.2003 | Villagers-23 | CRY & MLC |
| 10. | Core Group Meeting | MLC Meeting Hall | 17th & 18th Sep | Core Group of MLC & CRY team. | CRY & MLC |

OUT SIDE TRAINING /WORKSHOP / SEMINAR / MEETING

| SL NO | Name of the T/ W /S / M | VENUE | DATE / DURATION | PARTICIPATION | RESOURCE GROUP |
| --- | --- | --- | --- | --- | --- |
| 1 | Workshop on Innovative Pedagogical Approaches on Elementary Education. | S. N. Bose N C B Science, Kolkata. | 17th to 19th Aug ‘03 | Program Coordinator Education Supervisor | Science Communicator Forum. Kolkata. |
| 2. | Micro Finance Refresher Course | Science Centre, Purulia | 25.08.2003 | Program Coordinator | NABARD, Credit-Watch. |
| 3 | Educational Network Meeting | SSDC | 2nd & 3rd Sep 2003 | Project Holder | WBEN |
| 4. | Meeting on CSS | Jhargram | 8th September 2003 | PH, Motivator-2, P Cood, Supv. | WBEN, W Midnapore |
| 5. | Educational Network Meeting | Pally Unnayan Samity | 11th & 12th Sep 2003 | PH, Motiv-1, FM-3 | WBEN |
|  | Work shop on Mental Health & Life Skill Education | Don Bosco , Kolkata | 16th & 17th Sep 2003 | Edu Sup-2. Ext –Worker –1 | Mon Foundation |

COMMUNITY PARTICIPATION

By this process it can be understand the perception of organization on participation of community in a meeting.

COMMUNITY PARTICIPATION ON VILLAGE MEETING

| SL NO | Type of the Meeting | Topic discussed | Venue | Expected Participation | Participation | % of Attendance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Male | Female | Total |  |
| 1 | Village Meeting | Importance of CSS in Present situation | Mahukodor, Jhalda | 60 | 47 | -- | 47 | 78% |
| 2. |  | Role of VEC on CSS | Rerengtarn | 30 | 15 | 02 | 17 | 56% |
| 3. |  | Role of WBEN in CSS | Ghorabandha | 50 | 29 | 04 | 33 | 66% |
| 4. |  | Necessary of CSS | Laharia | 60 | 46 | 12 | 58 | 96% |
| 5. |  | Meeting on CSS. | Bagmundi | 30 | 18 | 04 | 22 | 73% |

CASE STUDY.

1a. BIRBHADRA CHALAK: - Birbhadra is son of Late. Manik Chalak.He was admitted in Bagmundi Pre-Primary Centre in 1994 April. Now he is studying in class VIII in Bagmundi High School. According to Smt. Abha Singh, the then teacher (now also), Bir was very shy in nature but he has some creativity skill from childhood. His father passed away when he was very little. He also loosed his brother last year. So, reality makes the shy Bir to mature “BIR” in his teenage. He helps his mother in every step. Bir want to continue his study as far as possible but he did not know how far it would continue! He is grateful to the pre- primary school from where he has got his basic education.   His future plan is to establish very soon to support his family.

1b. TUMPA SINGH: - Tumpa is daughter of Late. Radha Gobinda Singh. She was admitted in Bagmundi Pre-Primary centre in 1994 April. She was charming in nature and polite in behavior. Mrs. Abha Singh, her teacher was describing her nature. She was sincere in study. She was good in sports. As her father is no more, her mother was telling about Tumpa. Now Tumpa is a student of class VIII in Bagmundi High School. Tumpa is now a teenage girl; she can now understand the importance of education in her life. She can remember the day in Pre- Primary School. She will never forget her teacher, Abha Singh. Now as she is a student of class VIII, she wants to pass Madhyamik Examination with good marks. She wants to study more. No, now she has no any future plan.

1 c. Sagar Singh: - Son of Sri. Sandip Singh. Sagar Singh was admitted in Bagmundi Pre-Primary Centre in 1996 April. According to Mrs. Abha Singh, he was medium in study. He was very shy. He also has an affinity to sports. Now he is studying in class V in Bagmundi High School. Now, Sagar is quite mature and not so shy. He wants to continue his study as far as possible. He has no certain future plan but he wants to get job to support his family in future.

#### PART- II

# IMPACAT INDICATORS

#### SURVIVAL RIGHTS

|  |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a. Direct Action with Children | 1 | Under 5 mortality reduced. (No. Of Death case). |  | 05 | 00 |  |  |
|  | 2 | Pregnant women covered under health check – ups | 138 | 96 | 31 |  |  |
|  | 3 | Pregnant women covered under immunization | 138 | 84 | 31 |  |  |
|  | 4 | Pregnant mother received supplementary nutrition | 138 |  |  |  |  |
|  | 5 | Health check ups for children (0- 5 years) | 2249 | 267 | 307 |  |  |
|  | 6 | Common diseases reduce (Malaria & Diarrhea) |  | 03 | 02 |  |  |
|  | 7 | Occupational health problems reduced among children |  | 04 | 02 |  |  |
|  | 8 | New birth gets registered | 460 | 32 | 02 |  |  |
|  | 8A | Male |  | 19 | 01 |  |  |
|  | 8B | Female |  | 13 | 01 |  |  |
|  | 9 | Old and new birth gets registered |  | 56 |  |  |  |
|  | 9A | Male |  | 29 |  |  |  |
|  | 9B | Female |  | 27 |  |  |  |
| b. Action with community | 10 | Health committee formed |  | 04 | -- |  |  |
|  | 11 | Health committee active village |  | 01 | 01 |  |  |
|  | 12 | Local Dai trained | 15 | 17 | -- |  |  |
|  | 13 | PHC and sub center activated | HC-3, SHC-3, PHC-1 | PHC-1 | SHC-1 |  |  |
|  | 14 | New PHC and sub center demanded |  |  |  |  |  |
|  | 15 | Men covered under birth control | 743 | 67 | 71 |  |  |
|  | 16 | Women covered under birth control |  | 67 | 71 |  |  |
| c. Strengthening Local Self-Governance | 17 | Panchayat having health committee |  | 07 | 09 |  |  |
| SURVIVAL RIGHTS |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 18 | Panchayat active in health issues |  |  | 03 |  |  |
|  | 19 | Panchayat passed resolution demanding health rights |  |  |  |  |  |
|  | 20 | Panchayat having increased financial allocation on health |  |  |  |  |  |
| d. Networking and macro policy | 21 | Organization active in local network working on health issue |  |  |  |  |  |
|  | 22 | Network active in survival issue |  |  |  |  |  |
|  | 23 | Network analyze macro policy on survival |  |  |  |  |  |
|  | 24 | Organization with strong govt. interface |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  |  |  |  |  |  |  |
| a. Direct Action with Children | 25 | Children covered through pre-primary centers. | 2249 | 433 | 335 |  |  |
|  | 25A | Male |  | 237 | 181 |  |  |
|  | 25B | Female |  | 196 | 154 |  |  |
|  | 26 | Children covered through NFE Male- Female - |  |  |  |  |  |
|  | 27 | % of children from minorities and dalits get benefited through pre-primary and NFE |  | 38% | 41% |  |  |
|  | 28 | No. of pre-primary and NFE supported |  | 11 | 11 |  |  |
|  | 29 | 100% enrollment villages through formal school | 0 | 02 | 01 |  |  |
|  | 30 | Villages with 100% enrollment through education program |  |  |  |  |  |
|  | 31 | Formal schools with 100% retention |  |  |  |  |  |
| *Caste wise data to be maintained at regional level | 32 | Children mainstreamed sex and caste wise* | 2249 | 87 | 177 |  |  |
|  | 32A | Male | 1130 | 40 | 80 |  |  |
|  | 32B | Female | 1119 | 47 | 97 |  |  |
|  | 33 | Disabled children supported | 1 |  |  |  |  |
|  | 33A | Male | 1 |  |  |  |  |
|  | 33B | Female |  |  |  |  |  |
|  | 34 | Disabled children mainstreamed |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 34A | Male |  |  |  |  |  |
|  | 34B | Female |  |  |  |  |  |
|  | 35 | Formal school having provisions/ facilities for inclusive education for the disabled children |  |  |  |  |  |
| Sectors | I. No. | Impact Indicators |  |  |  |  |  |
| b. Action with community | 36 | No. of pre-primary (balwadi) and NFE teachers trained | 0 | 18 | 17 |  |  |
|  | 37 | Government Primary Schools Reactivated |  | NA | 02 |  |  |
|  | 38 | Demanding new govt. schools and classes |  |  |  |  |  |
|  | 39 | Govt. teachers trained |  |  |  |  |  |
|  | 40 | Para teachers placed in govt. schools: |  |  |  |  |  |
|  | 40A | Male |  |  |  |  |  |
|  | 40B | Female |  |  |  |  |  |
|  | 41 | Schools with active local education committee |  | 11 | 11 |  |  |
|  | 42 | Govt. school with active Panchayat VEC |  | 06 | 06 |  |  |
|  | 43 | CBOs active in education campaign |  | 07 | 07 |  |  |
|  | 44 | Education BLD in place |  | Yes | Yes |  |  |
|  | 45 | Partners with strong community mobilization |  | Yes | Yes |  |  |
|  | 46 | CBO active villages development |  | 07 | 07 |  |  |
|  | 47 | No. Of communities involved in action/ movement on other pre-dominant issues in relation to demanding education right |  | 04 | 04 |  |  |
| c. Strengthening Local Self-Governance | 48 | Partners with active govt. interface on education |  | 01 | 01 |  |  |
|  | 49 | Partners initiated Panchayat interface on education rights |  | 01 | 01 |  |  |
|  | 50 | Panchayat resolution demanding education rights |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 51 | VEC active Panchayat |  | 01 | 02 |  |  |
|  | 52 | Panchayat having increased financial allocation on education |  |  |  |  |  |
| d. Networking and macro policy influencing | 53 | Organization active in local network |  | Yes | 03 |  |  |
|  | 54 | Organization formed a local network |  |  | 01 |  |  |
|  | 55 | Organization analyses macro policies on education |  |  |  |  |  |
|  | 56 | Network analyses macro policies on education |  |  |  |  |  |
|  | 57 | Network active in education issue |  |  |  |  |  |
|  | 58 | Organization active in state network on education |  | Yes | Yes |  |  |
| III. Protection Rights |  |  |  |  |  |  |  |
| a. Direct Action with Children | 59 | Villages declared child labour free-up to 14 years |  |  | 01 |  |  |
|  | 60 | Villages declared 90% child labour – up to 14 years |  |  |  |  |  |
|  | 61 | Villages declared 80% child labour free |  |  |  |  |  |
|  | 62 | Villages declared child labour free-up to 18 years |  | 01 | 01 |  |  |
|  | 63 | Villages declared 90% child labour – up to 18 year |  |  |  |  |  |
|  | 64 | Villages declared 80% child labour free up to 18 years |  |  |  |  |  |
|  | 65 | Child labour covered under education program |  |  | 44 |  |  |
|  | 65A | Male |  |  | 22 |  |  |
|  | 65B | Female |  |  | 12 |  |  |
|  | 66 | Child labour removed from workplace and mainstreamed |  |  |  |  |  |
|  | 66A | Male |  |  |  |  |  |
|  | 66B | Female |  |  |  |  |  |
|  | 67 | Child labour removed from workplace and covered under NFE |  |  |  |  |  |
|  | 67A | Male |  |  |  |  |  |
|  | 67B | Female |  |  |  |  |  |
| III. Protection Rights |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 68 | Child labour covered under NFE but not removed from workplace | Laharia | 44 |  |  |  |
|  | 68A | Male |  | 32 |  |  |  |
|  | 68B | Female |  | 12 |  |  |  |
|  | 69 | Street children covered under education program |  |  |  |  |  |
|  | 69A | Male |  |  |  |  |  |
|  | 69B | Female |  |  |  |  |  |
|  | 70 | Street children under bridge schools |  |  |  |  |  |
|  | 70A | Male |  |  |  |  |  |
|  | 70B | Female |  |  |  |  |  |
|  | 71 | Street children mainstreamed |  |  |  |  |  |
|  | 71A | Male |  |  |  |  |  |
|  | 71B | Female |  |  |  |  |  |
|  | 72 | Street children provided institutional care |  |  |  |  |  |
|  | 72A | Male |  |  |  |  |  |
|  | 72B | Female |  |  |  |  |  |
|  | 73 | Street children home placed |  |  |  |  |  |
|  | 73A | Male |  |  |  |  |  |
|  | 73B | Female |  |  |  |  |  |
|  | 74 | Working children covered under education program |  |  |  |  |  |
|  | 74A | Male |  |  |  |  |  |
|  | 74B | Female |  |  |  |  |  |
|  | 75 | Working children removed from work force and mainstreamed |  |  |  |  |  |
|  | 75A | Male |  |  |  |  |  |
|  | 75B | Female |  |  |  |  |  |
|  | 76 | Working children covered under NFE but not removed from workforce |  |  |  |  |  |
|  | 76A | Male |  |  |  |  |  |
|  | 76B | Female |  |  |  |  |  |
|  | 77 | Working children covered under NFE and removed from workforce |  |  |  |  |  |
|  | 77A | Male |  |  |  |  |  |
|  | 77B | Female |  |  |  |  |  |
| Sectors | I. No. | Impact Indicators |  |  |  |  |  |
|  | 78 | Sexually abused children covered under counseling and medical help |  |  |  |  |  |
|  | 79 | Sexually abused children covered under referral services |  |  |  |  |  |
|  | 80 | Sexually abused children provided legal support |  |  |  |  |  |
|  | 81 | Sexually abused children provided institutional care |  |  |  |  |  |
|  | 82 | Child prostitutes removed from prostitution |  |  |  |  |  |
|  | 83 | Child prostitutes brought under education programs |  |  |  |  |  |
|  | 84 | Child prostitutes brought under health program |  |  |  |  |  |
|  | 85 | Child prostitutes brought under NFE |  |  |  |  |  |
|  | 86 | Child prostitutes brought under mainstream education |  |  |  |  |  |
|  | 87 | Child prostitutes brought under/provided institutional care |  |  |  |  |  |
|  | 88 | Child prostitutes rehabilitated |  |  |  |  |  |
| b. Action with community | 89 | No. of communities involved in action/movement in other pre-dominant issues in relation to demanding protection right |  |  |  |  |  |
|  | 90 | CBO’s active in campaign against child labour |  |  |  |  |  |
|  | 91 | BLD on child labour in place |  |  |  |  |  |
|  | 92 | Partners with strong community mobilization |  |  |  |  |  |
|  | 93 | CBO active on village protection |  |  |  |  |  |
|  | 94 | No. of sessions conducted on CSA among the reference group |  |  |  |  |  |
| c. Strengthening Local Self-Governance | 95 | Partners with active govt. interface on the problem of protection right |  |  |  |  |  |
|  | 96 | Partners initiated Panchayat interface on child labour problem |  |  |  |  |  |
|  | 97 | Panchayat resolution demanding protection rights for children |  |  |  |  |  |
|  | 98 | More financial allocation at Panchayat on livelihood issue for adult |  |  |  |  |  |
| d. Networking and macro policy influencing | 99 | Organization active in local network |  |  |  |  |  |
|  | 100 | Organization formed a local network |  |  |  |  |  |
|  | 101 | Network active on child labour issues |  |  |  |  |  |
|  | 102 | Network analyze macro policies on child labour |  |  |  |  |  |
|  | 103 | Organization with strong govt. interface |  |  |  |  |  |
|  | 104 | Organization active in state network on protection |  |  |  |  |  |

- Introduction.

- Program Goal

- Specific objectives

- PART- 1

- Outcome in terms of Quantitative changes (After 3rd quarter progress):

- Pre Primary Education Centre

- Primary Education Centre

- Right to Development.

- Right to Protection.

- Right to Survival.

- Holiday Camp

- In- house Training / Meeting / Workshop

- Outside Training / Meeting / Workshop

- Community Participation

- Contribution of Community

- Network Activities

- Core Group activities.

- CASE STUDY

- PART- 2: IMPACT INDICATORS

- INTRODUCTION: - Early childhood education in India is suffering from deficiencies of some proper procedure. On the one hand, millions of young children in lower income groups, especially rural and girl children, comprising nearly 40% of first grade entrants never complete primary school. Even among those who do, poorly qualified teachers, very high student-teacher ratios, inadequate teaching materials and outmoded teaching methods result in a low quality of education that often imparts little or no real learning. It is not uncommon for students completing six years of primary schooling in village public schools to lack even rudimentary reading and writing skills.

- PROGRAMME GOAL:

- Specific objectives:-

  - Ensure Children Rights for their Socio-education- cultural Development.

  - A Child of the age group of (0—18) yrs should be considered as a child.

  - The basic Health Programme should cover all Children.

  - An Appropriate and systematic Educational Network should built in entire district along with a sustainable Coordination with the rural people and all other parts of the society.

  - Campaign on Common School System (CSS) in every pocket of working areas.

  - Organize Holiday Camp to reduce the number of drop out children from school

- About Pre- Primary Education Centre.

- About Primary School

- About Developmental Rights

- About Survival Rights

- About Protection Rights

- Holiday Camp.

| Sl. No | Name of the Centre | Students | Average Attend. (In %) / Month | Average Working Days (%) | Animators (Teachers) | Grade |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Boy | Girl | Total | Boy | Girl |  | Trained | Un-trained |  |
| 1 | BAGHMUNDIH | 10 | 10 | 20 | 93 | 80 | 94 | 2 | -- | B |
| 2 | GHORABANDHA | 20 | 21 | 41 | 57 | 46 | 92 | 2 | -- | A |
| 3 | SINDHRI | 31 | 20 | 51 | 65 | 60 | 92 | 2 | -- | B |
| 4 | RERENGTANR | 14 | 18 | 32 | 54 | 79 | 90 | 2 | -- | A |
| 5 | JILINGTARN | 11 | 25 | 36 | 85 | 78 | 85 | 2 | -- | B |
| 6 | BURDA | 12 | 23 | 35 | 70 | 74 | 90 | 2 | -- | A |
| 7 | LAHARIA | 24 | 29 | 53 | 98 | 85 | 89 | 1 | 1 | B |
| 8. | BONGADA | 28 | 10 | 38 | 75 | - | 85 | 2 | - | A |
| 9. | SIRGI | 09 | 11 | 20 | 50 | 60 | 90 | -- | 1 | B |
| 10. | BELA | 14 | 09 | 23 | 63 | 81 | 80 | -- | 1 | B |
|  | Total | 173 | 176 | 349 | 71 | 64 |  |  |  |  |

A positive attitude has been observed among the parents toward this Primary School. Children showed their interest to their study.

| Sl. No | Name of the Centre | Students | Average Attend. (In %) / Month | Average Working Days (%) | Animators (Teachers) | Grade |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | Boy | Girl | Total | Boy | Girl |  | Trained | Un-trained |  |
| 1 | Aloke Kendra Primary School, Bagmundi. | 17 | 09 | 26 | 90 | 96 | 100 | -- | 3 | B |

OUTCOMES IN TERMS OF QUANTITATIVE CHANGES AFTER 3rd QUARTER (OCT – DEC ’03)

### DEVELOPMENT RIGHTS

| Sub | Parameter | Yearly Tar get | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieve | T | A | T | A | T | A |  |  |
| EDUCAT I ON | 1. No of Pre-Primary center run by the Orgn. | 11 |  | 11 |  | 11 | 11 | 10 | 10 |  | All students of Ayodhya school have been mainstreamed; hence the centre is now in pause situation. |  |
|  | 2. No of Non formal centers for school drop outs | NA |  | -- |  |  |  |  |  |  |  |  |
|  | 3. No of children attended by the Non- Formal centres. | NA |  | -- |  |  |  |  |  |  |  |  |
|  | 4. No of children covered under Pre –Primary. | 550 |  | 433 |  | 335 | 350 | 349 | 350 |  | Regular guardian meetings. |  |
|  | 5. No of children from Pre- Primary center admitted to Primary School | 177 |  | 87 |  | 177 |  |  |  |  |  |  |
|  | 6. No of children (5- 18 yrs) going to formal school. | 5269 |  |  |  | 3440 |  | 3440 |  |  |  | Some children drop out from the school. |
|  | 7. No of village with 100% enrollment | 2 | -- | -- |  | -- | 01 |  |  |  | Activities ongoing. | Lack of awareness of parents about the importance of education. |
|  | 8. No of Govt. Primary schools interface initiated. | 199 |  | 30 |  | 29 | 33 | 30 | 30 |  | Met & discussion with the Teachers. | Non-availability of teachers. |
|  | 9. No of Govt. Primary School Activated. | 14 |  | 02 |  | 02 | 02 | 01 | 02 |  | Bagmundi | Lack of interest of teachers |
|  | 10. No of local education committee (LEC). (For Pre-Primary) formed. | 11 |  |  |  | 09 | 02 | 02 | 02 |  | Rerengtarn, Ghorabandha. Meeting with the LEC. | Lack of awareness of the necessity of LEC. |

DEVELOPMENT RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan. | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieved | T | A | T | A | T | A |  |  |
| EDUCAT I ON | 11. No of local education committee activated. | 09 |  |  |  | 05 | 02 | 01 |  |  | Meeting & discussion Capacity Building through empowerment. | Due to harvesting season villagers have no time. |
|  | 12. No of Panchayat initiated. | 77 |  | 09 |  | 13 | 33 | 20 | 35 |  | Discussion. |  |
|  | 13. No of Panchayat activated in education issues. | 04 |  |  |  | 01 | 01 |  |  |  | Now process ongoing. | Lack of time of Panchayat members. |
|  | 14. No of village education committee interface initiated. | 66 |  |  |  | 23 | 22 | 04 | 20 |  | Meet and discussion | Lack of knowledge on the importance of VEC. |
|  | 15. No of village education committee activated. | 05 |  |  |  | 02 | 02 | 01 | 02 |  | Ghorabandha | Due to harvesting season villagers have no time. |
|  | 16. House hold visit | 5400 |  | 959 |  | 981 | 1000 | 1365 | 1000 |  | Visit house holds | Non-availability of householder. |
| NETWORK | 17. No of local organization/ Club activated through network | 15 |  |  |  | 03 | 04 | 01 | 03 |  | Jhalda Met & discussion. | Lack of capacity building of club members. |
|  | 18. Coordination with orgn. / Club. | 88 |  | 02 |  | 08 | 10 | 05 | 05 |  | Sindri,Ghorabandha, Bagmundi, Jhalda. | Non-availability of club members. |
|  | 19. Block Meeting | 01 |  |  |  |  | 01 | 01 | 02 |  | Jhalda. |  |
|  | 20. Rural Rally | 11 |  |  |  |  | 11 | 10 | 10 |  | On 14th Nov 03 |  |
|  | 21.Campaigning with Poster, walling, hat prachar etc. | 11 |  |  |  |  | 11 | 10 | 10 |  | On 14th Nov 03 (Children's day) |  |
|  | 22.Visit with the State Organization |  |  |  |  |  |  |  |  |  |  |  |
|  | 23. State Convention | 01 |  |  |  |  | 01 |  |  |  |  |  |
|  | 24. National Convention | 01 |  |  |  |  | 01 |  |  |  | On 16th to 18th Oct.’03 in Delhi. |  |

#### SURVIVAL RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieve | T | A | T | A | T | A |  |  |
| HEALTH AWARENESS | 1. No of children have birth registration certificate (0-14 yrs) | 175 |  | 32 |  | 02 | 15 | 89 | 52 |  | Communicating with Panchayat, guardians. |  |
|  | 2. No of children attended by health check up clinics (0-14yrs) | 100% |  | 307 |  | 127 | 180 | 185 | 185 |  | Communicating with the parents & health centre. | Lack of knowledge about the importance of check up |
|  | 3. No of children (0-5yrs) fully immunized. | 100% |  |  |  | 24 | 24 | 171 | 185 |  | Communicating with parents & HC |  |
|  | 4. No of pregnant mother covered under health care. | 100% |  | 96 |  | 31 | 96 | 119 | 119 |  | Communicating with HC & pregnant mother. | Careless about health care. |
|  | 5. No of mother covered under immunization. | 100% |  | 84 |  | 31 | 84 | 98 | 119 |  | Communicating with pregnant mother & HC |  |
|  | 6. No of eligible couple practices family planning measures. | 100% |  | 135 |  | 142 | 142 | 168 |  |  | Communicating with eligible couple & HC. | Generally men hesitate for permanent process. |
|  | 7. No of Panchayat interface initiated. | 33 |  | 09 |  | 16 | 18 | 15 | 17 |  | Meet and discussion |  |
|  | 8. No of Panchayat active in health issues. | 04 |  | -- |  | -- | 02 | 03 | 03 |  | Rerengtarn, Bagmundi, Sindri. |  |
|  | 9. No of Mahila Samities active in health issues. |  |  |  |  |  |  |  |  |  |  |  |
|  | 10. No. Of health center interface initiated. | 11 |  |  |  | 11 | 11 | 10 | 10 |  | Regularly visit |  |
|  | 11. No of health center active. | 04 |  |  |  | -- | 01 | 01 | 02 |  | Visit regularly | Lack of time of HW |
|  | 12. Communicate with health worker (HW) | 170 |  | 33 |  | 34 | 35 | 19 | 30 |  | Met with HW. | Non-availability of HW. |
|  | 13. No of Health meeting | 44 |  | -- |  | 04 | 10 | 03 | 07 |  | Met & discussion. | Lack of time of HW |
|  | 14. Meeting with health committee. | 33 |  | -- |  | -- | 11 | 03 | 08 |  | Process is ongoing | Lack of time of HC |
|  | 15. No of local orgn. Activated through network. | 11 |  | -- |  | -- | 02 | 01 | 01 |  | Process is ongoing | Lethargy of the local organization. |

#### PROTECTION RIGHTS

| Sub | Parameter | Yearly Target | QRT 1 | QRT-2 | QRT-3 | QRT - 4 | Achievement process / Type of Activity / Any Plan | Constraints Faced during the reporting quarter. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Target | Achieved | T | A | T | A | T | A |  |  |
|  | 1. No of child labour (5-18yrs) |  |  |  |  |  |  | 53 | 43 |  |  |  |
|  | 2. No. of village declared child labour free (upto 14 yrs) | 02 |  | -- |  | -- | 01 |  | 01 |  | Activities ongoing |  |
|  | 3. No of differently abled children with identity card. |  |  |  |  |  |  |  |  |  |  |  |
|  | 4. No of Self Help Group formed. |  |  |  |  |  |  |  |  |  |  |  |
|  | 5. No of Panchayat interface initiated. | 01 |  | -- |  | -- |  | -- |  |  | Activities ongoing |  |
|  | 6. No of Panchayat activated in protection issues. |  |  |  |  |  |  |  |  |  |  |  |
|  | 7. No of local orgn. Activated through network. | 04 |  |  |  | -- | 01 | -- | 01 |  | Process ongoing. |  |

With an objective to reduce the drop out children from class III & IV from school Holiday camp was started on June 2003 in 14 Govt Primary School. In 3rd Quarter in the month of October a serial number of holiday camps have been organized and number of follow up camps also followed.   Positive impacts are observed in these camps. The positive effect of the holiday camp is the attendance of more students in class. It was also observed among the children that a lot of interest has been grown regarding study and other affairs. The teachers are also getting interesting to teach the students. As a result of camp shyness of children are not seen among the children. They are interested to work in-group.

But to sustain this type of progress of the children is quite difficult for the teachers. It was observed in Follow up camp (on working days) that having only one teacher in some school (except 2 schools) it is quite impossible to tackle the entire students of class I, II, III, IV by one teacher. (In holiday camp only student of class III & IV attend the camp).

HOLIDAY CAMP AND ITS FOLLOW UP

| SL No. | Govt. Primary School | Date of Holiday Camp | Date of follow up camp |
| --- | --- | --- | --- |
| 1 | Deoli Primary School | 16th & 17th Oct 2003 | 15th Nov 2003 |
| 2 | Jordih Primary School | 16th & 17th Oct 2003 | 17th Nov 2003 |
| 3 | Atna Primary School | 16th & 17th Oct 2003 | 18th Nov 2003 |
| 4 | Rangamati Primary School | 18th & 19th Oct 2003 | 13th Nov 2003 |
| 5 | Peretorang Primary School | 18th & 19th Oct 2003 | 20th Nov 2003 |
| 6 | Noadih Primary School | 18th & 19th Oct 2003 | 19th Nov 2003 |
| 7 | Mukrub Primary School | 18th & 19th Oct 2003 | 12th Nov 2003 |
| 8 | Raidih Primary School | 18th & 19th Oct 2003 | 11th Nov 2003 |
| 9 | Patahesal Primary School | 20th & 21st Oct 2003 | 3rd Nov 2003 |
| 10 | Suisa Primary School | 20th & 21st Oct 2003 | 4th Nov 2003 |
| 11 | Marcha Primary School | 20th & 21st Oct 2003 | 5th Nov 2003 |
| 12 | Parshidih Primary School | 22nd & 23rd Oct 2003 | 6th Nov 2003 |
| 13 | Simali Primary School | 22nd & 23rd Oct 2003 | 7th Nov 2003 |
| 14 | Saridih Primary School | 22nd & 23rd Oct 2003 | 10th Nov 2003 |

###### IN-HOUSE TRAINING / WORKSHOP / MEETING

| Sl. No | PROGRAMME | VENUE | DATE / DURATION | PARTICIPANTS | RESOURCE GROUP |
| --- | --- | --- | --- | --- | --- |
| 1 | Monthly Teachers meeting | MLC Meeting Hall | 29.10.2003 27.11.2003 14.12.2003 | Animator-18, Sup-1, Motivator-1, P.Cord, | MLC - PH |
| 2 | Subject Base meeting i) CSS ii) SSA iii) SSK | MLC Meeting Hall | 3 meetings | Animator-18, Sup-2, Motivator-1, P.Cord, | MLC-PH |
| 3 | WBEN Meeting Discussion | MLC Meeting Hall | 14.12.2003 | Animator-18, Sup-2, Organ, P.Cord, | MLC PH, Motivat |
| 4 | CORE Group Meeting | MLC Meeting Hall | 29.10.2003 10.11.2003 14.12.2003 | CORE GROUP | CORE TEAM |
| 5 | Educational Network Meeting | Begunkodor, Jhalda II Block | 12.11.2003 13.11.2003 14.11.2003 | Motivator, Villagers- 51. Student –12 | PH |
| 6 | SGSY & SHG Meeting | Balarampur Block | 18.12.2003 | Project Coordinator | BDO, EOP |

OUT SIDE TRAINING /WORKSHOP / SEMINAR / MEETING

| SL NO | Name of the T/ W /S / M | VENUE | DATE / DURATION | PARTICIPATION | RESOURCE GROUP |
| --- | --- | --- | --- | --- | --- |
| 1 | NAFRE Congress | Delhi | 16th to 18th Oct ‘03 | State conv, Dist conv. Educational forum member – 2 | NAFRE |
| 2. | Education Network Meeting | Nimta, Kolkata | 9th Nov ‘03 | Project Holder | WBEN |
| 3 | Account Training | Digha | 17th to 20th Nov ‘03 | Accountant | CRY |
| 4. | NAFRE Meeting | Delhi | 21st to 25th Nov ‘03 | Project Holder | NAFRE |
| 5. | RC (PSP) Meeting | Puri | 1st to 3rd Dec ‘03 | Project Holder | CRY |
| 6. | WBEN Meeting | Mogholpur, Hoogly | 10th to 12th Dec ‘03 | Project Holder, Motivator, Asst Supervisor, Forum member. | WBEN |
| 7 | WBEN Meeting | Dhyanashram,Kolkata | 15th to 18th Dec ‘03 | Project Holder, Motivator, Asst Sup. | WBEN |
| 8 | WBEN Meeting | Jhargram | 20th Dec ‘03 | Project Holder | WBEN |
| 9 | WBEN Meeting | Jhargram & Kanthi | 21st Dec ‘03 | Project Holder | WBEN |

COMMUNITY PARTICIPATION IN DIFFERENT MEETING / CAMP

| SL No | Meeting / Camp | Topic discussed | Venue | Total Expected participants | Total Participated | Percentage of Attendance |
| --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | Male | Female | Total |  |
| 1 | Education meeting Parents meeting | Change of school time Regularity of students CSS | Sirgi, Bela, Burda, Sindri | 120 | 53 | 42 | 95 | 79% |
| 2 | Village meeting | Birth certificate CSS New School construction | Bagmundi, Ghorabandha Jilingtarn, Laharia, Bongada Ajodhya | 240 | 136 | 40 | 176 | 73% |
| 3 | Health meeting | Diarrhoea Malaria, Birth certificate | Burda, Bongada, Laharia Sindri | 160 | 50 | 71 | 121 | 75% |
| 4 | Health Awareness camp | Malaria, Diarrhoea, Birth certificate & Registration. | Bagmundi, Laharia, Kudna | 150 | 4 | 93 | 97 | 64% |

CONTRIBUTION OF COMMUNITY and HOME VISIT

| Item | Bagmundi | Ghorabandh | Sindri | Rerengtarn | Burda | Laharia | Bela | Sirgi | Jilingtarn | Bongada | Bagmundi Pri school | Total Rs. |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Collection of fees |  | 110.00 | 65.00 | 35.00 |  |  |  |  |  |  |  | 210.00 |
| Contribution in program | 70.00 |  |  | 50.00 |  |  |  |  |  |  |  | 120.00 |
| Home visit | 90 | 148 | 226 | 260 | 82 | 70 | 105 | 54 | 110 | 168 | 52 | 1365 |

NETWORK ACTIVITIES FROM OCT TO DEC 2003)

BY MANDRA LIONS CLUB, BAGMUNDI, PURULIA.

| Sl No. | Date | Venue | Programme/Issue | Discussion | Organized by | Participants | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 06.11.2203 | Jhalda, Hat tala | Role of Students in CSS. | What is CSS? Importance of CSS. Role of Students in CSS. | Mandra Lions Club, Bagmundi, | 12 |  |
| 2 | 07.11.2003 | Balarampur | What is WBEN? Necessary of CSS. | Details of CSS. Impact of Privatization on Rural Education System. | Mandra Lions Club, Bagmundi, | 19 | Rural people Show their interest. |
| 3 | 07.11.2003 | Jhalda, | Role of Club in CSS. | CSS in details. Role of clubs in CSS. | Mandra Lions Club, Bagmundi, | 23 | Agreed to form a network to spread the idea of CSS. |
| 4 | 09.11.2003 | Ghorabandha | Meeting on CSS with the villagers. | What is CSS? What is its importance? Impact of Privatization on rural life. | Mandra Lions Club, Bagmundi, | 24 | Village people have more interest on CSS. |
| 5 | 11.11.2003 | Sindri village. | Role of villagers in CSS. | Details on CSS. Impact of Privatization in rural villages. Role of villagers in CSS. | Mandra Lions Club, Bagmundi, | 20 | Need more meetings to make them understand. |

| Sl No. | Date | Venue | Programme/Issue | Discussion | Organized by | Participants | Remarks |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 6 | 12.11.2003 13.11.2003 14.11.2003 | 6 villages of Jhalda II Block. Begunkodor Chatambari Laxipur Supurdi- Brindabanpur Mamudih Murguma | What is CSS? What is WBEN? | Details on CSS and WBEN. | Mandra Lions Club, Bagmundi, | Total 165 | Need more meetings to make them understand. |
| 7 | 15.11.2003 | Rerengtarn | Role of villagers in CSS. | Importance of CSS. | MLC | 22 |  |
| 8 | 18.11.2003 | WBEN office, Kolkata. | Meeting with the participants of NAFREE Congress in Delhi. |  | WBEN | 15 apx |  |
| 9 | 21st –25th Nov 2003 | Delhi | NAFRE Meeting | Entire issues. | NAFRE |  |  |
| 10 | 1st – 3rd Dec 2003 | Puri | RC (PSP) Meeting | Regional Committee meeting | WBEN |  |  |
| 10 | 07.12.03 | MLC HALL | Sharing of NAFREE Congress in Delhi | Sharing about the Congress. | MLC | 15 | Need more meetings |
| 11 | 10th – 12th Dec 2003 | Mogholpur. Hoogly | WBEN Meeting | Advocacy on Education rights | WBEN |  |  |
| 12 | 15th –18th Dec 2003 | Dhyanashram. Kolkata | WBEN Meeting | Advocacy on Education, CSS | WBEN |  |  |
| 13 | 20.12.2003 | Jhargram | WBEN Meeting | Education and CSS | WBEN |  |  |
| 14 | 21.12.2003 | Jhargram & Kanthi | WBEN Meeting | CSS and Advocacy on Education rights | WBEN |  |  |

#### ABOUT CORE GROUP OF MANDRA LIONS CLUB

Since previous quarter (2nd ) Mandra Lions Club has formed a CORE GRUP(CG) comprising 10 members of this organization. The main objective of formation of CG is to formulate the organizational work smoothly with proper decision-making. CG   has sat once in a month. Actually this quarter was the initial stage of CG formation. By these 3 consecutive meeting CG has discussed on the roles and responsibility of CG in

absence of Secretary. Discussed on the power and its utilization of CG. In the last CG meeting (14.12.2003) following decision has been taken-

- CG will sit on Friday of the week to monitor the regular weekly reports.

- CG will sit once in a month on Last Friday of each month to discuss the all problems and possibilities.

- CG will make a Schedule for Secretary for visit the ongoing program of the organization on priority basis.

- CG may re-shuffle the stuff for required organizational program.

- CG member will visit the different fields of the organization.

- CG will monitor and analyze all the programs run by the organization.

- CG will regularly maintain the resolution copy.

CASE STUDY

PURAN CHANDRA PARAMANIK:  He is a student of class III of Deoli Primary School. During 1st Holiday Camp in the month of June 2003, he was very shy and introverts type. He didn’t talk with his friends and keep himself in his own shell. He never used to answer any question of the teacher.

But after continuous holiday camp by the teacher, it was observed that Puran is conveying his thoughts with his friends and giving attention in his study. Not only he is progressing in his study, but also he is participating in Recitation and other cultural activities. The most surprising activity by him was playing a short drama with his friend. Now he is very favorite student of the teacher.

#### PART- II

IMPACAT INDICATORS

MANDRA LIONS CLUB, BAGMUNDI

SURVIVAL RIGHTS

|  |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
| --- | --- | --- | --- | --- | --- | --- | --- |
| a. Direct Action with Children | 1 | Under 5 mortality reduced. (No. Of Death case). |  | 05 | 00 | 07 |  |
|  | 2 | Pregnant women covered under health check – ups | 138 | 96 | 31 | 119 |  |
|  | 3 | Pregnant women covered under immunization | 138 | 84 | 31 | 98 |  |
|  | 4 | Pregnant mother received supplementary nutrition | 138 |  |  |  |  |
|  | 5 | Health check ups for children (0- 5 years) | 2249 | 267 | 307 | 185 |  |
|  | 6 | Common diseases reduce (Malaria & Diarrhea) |  | 03 | 02 | 02 |  |
|  | 7 | Occupational health problems reduced among children |  | 04 | 02 | -- |  |
|  | 8 | New birth gets registered | 460 | 32 | 02 | 44 |  |
|  | 8A | Male |  | 19 | 01 | 19 |  |
|  | 8B | Female |  | 13 | 01 | 25 |  |
|  | 9 | Old and new birth gets registered |  | 56 |  | 45 |  |
|  | 9A | Male |  | 29 |  | 21 |  |
|  | 9B | Female |  | 27 |  | 24 |  |
| b. Action with community | 10 | Health committee formed |  | 04 | -- | -- |  |
|  | 11 | Health committee active village |  | 01 | 01 | 01 |  |
|  | 12 | Local Dai trained | 15 | 17 | -- |  |  |
|  | 13 | PHC and sub center activated | HC-3, SHC-3, PHC-1 | PHC-1 | SHC-1 | SHC-1 |  |
|  | 14 | New PHC and sub center demanded |  |  |  |  |  |
|  | 15 | Men covered under birth control | 743 | 67 | 71 | 69 |  |
|  | 16 | Women covered under birth control |  | 67 | 71 | 99 |  |
| c. Strengthening Local Self-Governance | 17 | Panchayat having health committee |  | 07 | 09 | 09 |  |
| SURVIVAL RIGHTS |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 18 | Panchayat active in health issues |  |  | 03 | 03 |  |
|  | 19 | Panchayat passed resolution demanding health rights |  |  |  |  |  |
|  | 20 | Panchayat having increased financial allocation on health |  |  |  |  |  |
| d. Networking and macro policy | 21 | Organization active in local network working on health issue |  |  |  |  |  |
|  | 22 | Network active in survival issue |  |  |  |  |  |
|  | 23 | Network analyze macro policy on survival |  |  |  |  |  |
|  | 24 | Organization with strong govt. interface |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  |  |  |  |  |  |  |
| a. Direct Action with Children | 25 | Children covered through pre-primary centers. | 2249 | 433 | 335 | 349 |  |
|  | 25A | Male |  | 237 | 181 | 173 |  |
|  | 25B | Female |  | 196 | 154 | 176 |  |
|  | 26 | Children covered through NFE Male- Female - |  |  |  |  |  |
|  | 27 | % of children from minorities and dalits get benefited through pre-primary and NFE |  | 38% | 41% | 46% |  |
|  | 28 | No. of pre-primary and NFE supported |  | 11 | 11 | 10 |  |
|  | 29 | 100% enrollment villages through formal school | 0 | 02 | 01 | 01 |  |
|  | 30 | Villages with 100% enrollment through education program |  |  |  |  |  |
|  | 31 | Formal schools with 100% retention |  |  |  |  |  |
| *Caste wise data to be maintained at regional level | 32 | Children mainstreamed sex and caste wise* | 2249 | 87 | 177 | -- |  |
|  | 32A | Male | 1130 | 40 | 80 | -- |  |
|  | 32B | Female | 1119 | 47 | 97 | -- |  |
|  | 33 | Disabled children supported | 1 |  |  |  |  |
|  | 33A | Male | 1 |  |  |  |  |
|  | 33B | Female |  |  |  |  |  |
|  | 34 | Disabled children mainstreamed |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 34A | Male |  |  |  |  |  |
|  | 34B | Female |  |  |  |  |  |
|  | 35 | Formal school having provisions/ facilities for inclusive education for the disabled children |  |  |  |  |  |
| Sectors | I. No. | Impact Indicators |  |  |  |  |  |
| b. Action with community | 36 | No. of pre-primary (balwadi) and NFE teachers trained | 0 | 18 | 17 | -- |  |
|  | 37 | Government Primary Schools Reactivated |  | NA | 02 | 04 |  |
|  | 38 | Demanding new govt. schools and classes |  |  |  |  |  |
|  | 39 | Govt. teachers trained |  |  |  |  |  |
|  | 40 | Para teachers placed in govt. schools: |  |  |  |  |  |
|  | 40A | Male |  |  |  |  |  |
|  | 40B | Female |  |  |  |  |  |
|  | 41 | Schools with active local education committee |  | 11 | 11 | 10 |  |
|  | 42 | Govt. school with active Panchayat VEC |  | 06 | 06 | 01 |  |
|  | 43 | CBOs active in education campaign |  | 07 | 07 | 01 |  |
|  | 44 | Education BLD in place |  | Yes | Yes | Yes |  |
|  | 45 | Partners with strong community mobilization |  | Yes | Yes | Yes |  |
|  | 46 | CBO active villages development |  | 07 | 07 | 01 |  |
|  | 47 | No. Of communities involved in action/ movement on other pre-dominant issues in relation to demanding education right |  | 04 | 04 | -- |  |
| c. Strengthening Local Self-Governance | 48 | Partners with active govt. interface on education |  | 01 | 01 | 01 |  |
|  | 49 | Partners initiated Panchayat interface on education rights |  | 01 | 01 | 01 |  |
|  | 50 | Panchayat resolution demanding education rights |  |  |  |  |  |
| II. DEVELOPMENT RIGHT |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 51 | VEC active Panchayat |  | 01 | 02 | 02 |  |
|  | 52 | Panchayat having increased financial allocation on education |  |  |  |  |  |
| d. Networking and macro policy influencing | 53 | Organization active in local network |  | Yes | 03 | 04 |  |
|  | 54 | Organization formed a local network |  |  | 01 | 01 |  |
|  | 55 | Organization analyses macro policies on education |  |  |  |  |  |
|  | 56 | Network analyses macro policies on education |  |  |  |  |  |
|  | 57 | Network active in education issue |  |  |  |  |  |
|  | 58 | Organization active in state network on education |  | Yes | Yes | Yes |  |
| III. Protection Rights |  |  |  |  |  |  |  |
| a. Direct Action with Children | 59 | Villages declared child labour free-up to 14 years |  |  | 01 | -- |  |
|  | 60 | Villages declared 90% child labour – up to 14 years |  |  |  |  |  |
|  | 61 | Villages declared 80% child labour free |  |  |  |  |  |
|  | 62 | Villages declared child labour free-up to 18 years |  | 01 | 01 | -- |  |
|  | 63 | Villages declared 90% child labour – up to 18 year |  |  |  |  |  |
|  | 64 | Villages declared 80% child labour free up to 18 years |  |  |  |  |  |
|  | 65 | Child labour covered under education program |  |  | 44 | 53 |  |
|  | 65A | Male |  |  | 22 | 24 |  |
|  | 65B | Female |  |  | 12 | 29 |  |
|  | 66 | Child labour removed from workplace and mainstreamed |  |  |  |  |  |
|  | 66A | Male |  |  |  |  |  |
|  | 66B | Female |  |  |  |  |  |
|  | 67 | Child labour removed from workplace and covered under NFE |  |  |  |  |  |
|  | 67A | Male |  |  |  |  |  |
|  | 67B | Female |  |  |  |  |  |
| III. Protection Rights |  | Activities | Baseline (Dec- 2002) | QRT-I | QRT-II | QRT-III | QRT-IV |
|  | 68 | Child labour covered under NFE but not removed from workplace | Laharia | 44 |  | 53 |  |
|  | 68A | Male |  | 32 |  | 24 |  |
|  | 68B | Female |  | 12 |  | 29 |  |
|  | 69 | Street children covered under education program |  |  |  |  |  |
|  | 69A | Male |  |  |  |  |  |
|  | 69B | Female |  |  |  |  |  |
|  | 70 | Street children under bridge schools |  |  |  |  |  |
|  | 70A | Male |  |  |  |  |  |
|  | 70B | Female |  |  |  |  |  |
|  | 71 | Street children mainstreamed |  |  |  |  |  |
|  | 71A | Male |  |  |  |  |  |
|  | 71B | Female |  |  |  |  |  |
|  | 72 | Street children provided institutional care |  |  |  |  |  |
|  | 72A | Male |  |  |  |  |  |
|  | 72B | Female |  |  |  |  |  |
|  | 73 | Street children home placed |  |  |  |  |  |
|  | 73A | Male |  |  |  |  |  |
|  | 73B | Female |  |  |  |  |  |
|  | 74 | Working children covered under education program |  |  |  |  |  |
|  | 74A | Male |  |  |  |  |  |
|  | 74B | Female |  |  |  |  |  |
|  | 75 | Working children removed from work force and mainstreamed |  |  |  |  |  |
|  | 75A | Male |  |  |  |  |  |
|  | 75B | Female |  |  |  |  |  |
|  | 76 | Working children covered under NFE but not removed from workforce |  |  |  |  |  |
|  | 76A | Male |  |  |  |  |  |
|  | 76B | Female |  |  |  |  |  |
|  | 77 | Working children covered under NFE and removed from workforce |  |  |  |  |  |
|  | 77A | Male |  |  |  |  |  |
|  | 77B | Female |  |  |  |  |  |
| Sectors | I. No. | Impact Indicators |  |  |  |  |  |
|  | 78 | Sexually abused children covered under counseling and medical help |  |  |  |  |  |
|  | 79 | Sexually abused children covered under referral services |  |  |  |  |  |
|  | 80 | Sexually abused children provided legal support |  |  |  |  |  |
|  | 81 | Sexually abused children provided institutional care |  |  |  |  |  |
|  | 82 | Child prostitutes removed from prostitution |  |  |  |  |  |
|  | 83 | Child prostitutes brought under education programs |  |  |  |  |  |
|  | 84 | Child prostitutes brought under health program |  |  |  |  |  |
|  | 85 | Child prostitutes brought under NFE |  |  |  |  |  |
|  | 86 | Child prostitutes brought under mainstream education |  |  |  |  |  |
|  | 87 | Child prostitutes brought under/provided institutional care |  |  |  |  |  |
|  | 88 | Child prostitutes rehabilitated |  |  |  |  |  |
| b. Action with community | 89 | No. of communities involved in action/movement in other pre-dominant issues in relation to demanding protection right |  |  |  |  |  |
|  | 90 | CBO’s active in campaign against child labour |  |  |  |  |  |
|  | 91 | BLD on child labour in place |  |  |  |  |  |
|  | 92 | Partners with strong community mobilization |  |  |  |  |  |
|  | 93 | CBO active on village protection |  |  |  |  |  |
|  | 94 | No. of sessions conducted on CSA among the reference group |  |  |  |  |  |
| c. Strengthening Local Self-Governance | 95 | Partners with active govt. interface on the problem of protection right |  |  |  |  |  |
|  | 96 | Partners initiated Panchayat interface on child labour problem |  |  |  |  |  |
|  | 97 | Panchayat resolution demanding protection rights for children |  |  |  |  |  |
|  | 98 | More financial allocation at Panchayat on livelihood issue for adult |  |  |  |  |  |
| d. Networking and macro policy influencing | 99 | Organization active in local network |  |  |  |  |  |
|  | 100 | Organization formed a local network |  |  |  |  |  |
|  | 101 | Network active on child labour issues |  |  |  |  |  |
|  | 102 | Network analyze macro policies on child labour |  |  |  |  |  |
|  | 103 | Organization with strong govt. interface |  |  |  |  |  |
|  | 104 | Organization active in state network on protection |  |  |  |  |  |

# Text boxes

# VILL + PO – BAGMUNDI

SARADAPALLY

DIST- PURULIA, PIN- 723152

E- mail- mlc_bagmundi@rediffmail.com

Universal Elementary Education for All through Triangular Relationship among – the Child, the Teacher and the Community.

Outcome in terms of Quantitative Changes (After 2ND Qrt- July—Sep 2003)

#### ABOUT PRE-PRIMARY CENTRE

### Details About Pre- Primary Education Centre

#### About Primary Education Centre

Need Trained Animator (Teacher)

### HOLIDAY CAMP

# VILL + PO – BAGMUNDI

SARADAPALLY

DIST- PURULIA, PIN- 723152

E- mail- mlc_bagmundi@rediffmail.com

Universal Elementary Education for All through Triangular Relationship among – the Child, the Teacher and the Community.

Outcome in terms of Quantitative Changes (After 3rd  Qrt- Oct—Dec 2003)

### Details About Pre- Primary Education Centre

#### About Primary Education Centre

### HOLIDAY CAMP