Proposals

Sikshana Foundation Phase IV (Anekal)

May 2009

Project: Replication of Sikshana in a third node in the State of Karnataka

Sikshana is a unique effort started by the Sivasri Charitable Trust that aims at improving learning levels in the government primary schools through better access and delivery of education. The program has grown in five years to cover 135 schools and 20,000 kids, becoming one of the top such interventions in the State of Karnataka. Sikshana aims to build a participatory and gender-sensitive teaching/learning approach to foster critical thinking and problem-solving skills.

Sikshana aims to improve the quality of education in Government primary schools at a typical cost of Rs. 30,000 per annum per school. The improvement is measured in quantified scales in each school under standard test conditions. The program is essentially focused on decentralization and empowerment of the adopted schools.  Sikshana acts primarily as a facilitator and not as provider of solutions.

Rationale of the project:

Decentralization and empowerment of the schools can lead to a healthy public education system. At present, the expense incurred by the government in educating a child in this system works out to anywhere between Rs 7000 to Rs 10,000 per annum. For a typical school of 150 kids, this amounts to Rs 10 lakhs or more. A program which seeks to get optimum learning levels at a cost of Rs 50,000- inclusive of the direct and monitoring costs- is an eminently desirable one, if the targets are realized.

The failure of the public education system in India is well documented in various studies and also the academic statistics maintained by the state education department finds the government schools lacking the minimum standards prescribed by the state itself.

The Sikshana approach has been significantly successful in two clusters of schools already adopted by Sikshana in and around Bangalore City and neighboring Kanakapura taluk.  The current proposal seeks to extend its scope to a third cluster in Bangalore called Anekal Taluk in order to establish its validity statistically over a larger number of schools and in all environments.

Objective

To improve the academic standards in the government higher primary schools specifically in the areas of ability to read and write, basic computation and expression as per the minimum learning levels defined by the department of education.

Target Group

The program targets children studying in Government primary schools of the age group 5 to 13. These kids belong to the most deprived sections of the society as parents who have the means to raise as little as Rs 50 per month normally choose to place their children in private schools.

Project Location

The location will be Anekal Taluk, Bangalore 20 higher primary schools in that school district will be selected for the project and an MOU with the Department of Education has already been signed to implement the Sikshana Project at these schools.

Deliverables

- Fluency in reading and writing non –text book Kannada of the appropriate level in 3rd and 7th Standard (year 1 estimated impact on 700 children)

- Basic Computational skills with two digits in III Standard (year 1 estimated impact on 300 children)

- Lingual skills in English at IV Standard: Vocabulary of 500 words and ability to construct simple sentences (year 1 estimated impact on 300 children)

- Attain 65% in APF model testing as adopted by Dept of Education or 10% increase every year , as applicable

- 90% plus students to get Grades B or above in all subjects in VII Standard Final Examinations (year 1 estimated impact on 500 children)

- Time schedule:  Bench marks to be attained in two years and maintained in the Third.

An estimated 2500 children will be the target student population during the duration of the project.

Duration

3 years

Sustainability Plan

Sikshana is essentially a program aimed at evolving a sustainable and replicable model for the public education system at the primary level. It has been in existence for about five years, with the coverage increasing from three in the first year of its operation to 135 in the fifth. Sikshana has been able to show significant and measurable improvement in the learning levels at a typical cost of not more than Rs 30,000 per annum in a typical school of 150 kids.

The schools which have gone through this program for three years are showing encouraging results, indicating that it is feasible to have a permanent and lasting impact over a 5 to 7 year period.

Sikshana feels that sustainability in the field can be ensured through the following options:

- The enhancements achieved may be irreversible and the school may not need continued support on the same scale. The presence of some schools of excellence within the public school system proves this point.

- The school may need substantially less external resources to maintain the momentum, which may be within the reach of the local community.  It has been seen that some of the communities in the school zone have shown the capability to raise such amounts, over and above the amount which Sikshana have deployed.

- And thirdly the department and the government are closely watching the impact of the intervention and if shown as a successful model then there is a good possibility that they may cover the incremental expense to implement the Sikshana practices.

Proposed Budget

| Summary | 1st year | 2nd year | 3rd year |
| --- | --- | --- | --- |
| Program Expenses | 6,00,000 | 5,00,000 | 4,00,000 |
| Common Expenses | 1,00,000 | 80,000 | 60,000 |
| Monitoring Expenses | 1,80,000 | 1,80,000 | 90,000 |
| Cost of a Program Manager | 50,000 | 50,000 | 50,000 |
| Admin and Misc Costs | 40,000 | 40,000 | 40,000 |
| Scholarships |  | 1,80,000 | 1,80,000 |
| Contingencies | 10,000 | 10,000 | 10,000 |
| Total | Rs. 9,80,000 | 10,40,000 | 8,30,000 |

Work Plan

| Goal: To improve the academic standards in the government higher primary schools specifically in the areas of ability to read, write, basic computation and expression as per the minimum learning level defined by the department of education |
| --- |
| Measurable Outcome(s): Fluency in reading and writing non –text book Kannada of the appropriate level in 3rd and 7th Standard Basic Computational skills with two digits in III Standard Lingual skills in English at IV Standard: Vocabulary of 500 words and ability to construct simple sentences Attain 65% in APF model testing as adopted by Dept of Education or 10% increase every year , as applicable 90% plus students to get Grades B or above in all subjects in VII Standard Final Examinations The same activities are planned for the 2nd and 3rd year with minor modifications in the program as necessary depending on the feedback from the 1st year implementation of the program. |
| Major Objectives | Key Tasks | Lead Person | Timeframe (Start and End Date by Month) Apr-Jun Jul-Sep Oct-Dec Jan-Mar |
| 1 TQM (Total Quality Management) Concepts to be introduced in all the schools | a) TQM training program for all teachers (current estimate is 600 teachers from 105 schools) | Sikshana TQM Training Staff | Conduct a TQM workshop and have schools draft their goals | Monitor milestones | Monitor milestones | Feedback TQM session at end of the academic year |  |
|  | b) Goals and Vision statement to be displayed in each school | School Staff | Create the display board with vision/goals | Check progress against set milestones | Check progress against set milestones | Report goals achieved at end of the year |  |
| 2. Fluency in reading non-text Kannada and English at the appropriate level (current estimate is that 4000 children will be impacted every year in 3rd and 7th class from the 105 schools) | Subscribe Kannada and English newspaper to the school and use them in the school assembly daily by having children read the news headlines | School Staff | Start the program at the beginning of the school year | Continue the program | Continue the program | Continue the program |  |
|  | Take children to large book stores and let them create their own library | School Staff and Sikshana Mentor | Have select children from class 5,6 and 7 to create their own library. Those students become library monitors | Library monitors ensures all children read at least one book per week. Class 7 students summarize in one page each book they read | Library monitors ensures all children read at least one book per week. Class 7 students summarize in one page each book they read | Library monitors ensures all children read at least one book per week. Class 7 students summarize in one page each book they read |  |
|  | Verify the compliance to the program by the school staff | Sikshana Mentor | Create a baseline for class 3 and 7 for each of the school | Monitor progress | Monitor progress | Report end of year progress |  |
| 3) Improve the overall learning levels in the school. Measurement parameters: 1. 65% or above in the APF model testing by independent agency 2. 90% of the children in class 7 will score B or above in the final exam | a)Implementation of the following motivational programs of Sikshana : 1. Sheet bank initiative 2. Spot prizes 3. Delhi trip for quiz winners 4. Annual prizes 5. Educational tour 6. Teaching Aids 7. Computer initiative 8. Para teachers 9. Other initiatives as determined by the school staff with an eye towards increasing the learning levels in that school. | School Staff | Sheet bank initiative Spot Prizes Teaching Aids Computer initiative Para teachers Other teacher initiatives | Sheet bank initiative Spot Prizes Teaching Aids Computer initiative Para teachers Delhi trip quiz and tour Other teacher initiatives | Sheet bank initiative Spot Prizes Teaching Aids Computer initiative Para teachers Educational tour Other teacher initiatives | Sheet bank initiative Spot Prizes Teaching Aids Computer initiative Para teachers Annual prizes Other teacher initiatives |  |
|  | b)Compliance of the program | Sikshana Mentor | Monitor and suggest changes | Monitor and suggest changes | Monitor and suggest changes | Monitor and suggest changes |  |
|  | c) Assessments | Independent testing agency | First Assessment |  |  | Second Assessment and report |  |
|  | d)Department Exams | School Staff |  | First Semester Exams |  | Final Exam and report |  |

4. PROJECT MONITORING & EVALUATION

- Monitoring and evaluation, both programmatic and financial will be conducted on a quarterly basis to ensure that intervention is on track to meet desired impact. Cheques for the project will be released in two instalments. Each disbursement will be audited and then the next instalment will be released.

- A six monthly programme report on the project will be provided to donor.

- A final financial utilization certificate that lists out all the budget heads under the specific programme and its utilization will be provided to donor on completion of the term.

- A final programme report on the project will be provided to donor. The report will detail activities conducted in the project duration, their impact and recommendations for future support.

Addenda 1

Program Expenses :  These are the funds given to each of the schools to implement the Sikshana program. At Rs.30,000 per school of average strength of 150, the total cost for running Sikshana in 20 schools will be Rs. 6,00,000. The break up of the expenses is as below.

| School Expenses per school | Cost in Rs. |
| --- | --- |
| Library / Paper for Writing | 4000 |
| Annual Prizes | 2000 |
| Spot Prizes | 2000 |
| School Functions | 3000 |
| Tours / Field Visits | 3000 |
| Teaching Aids | 3000 |
| Class Tests/ Examinations | 4000 |
| School Maintenance | 1000 |
| Induction of Para – Teachers | 5000 |
| Other Discretionary Efforts | 3000 |
| Total | 30,000 |

Common Expenses : There are the expenses incurred on behalf of all the schools. These typically include TQM training for the teaching staff, Annual day for all Sikshana Schools etc.

This cost is typically Rs. 5000/- per school when programs are run in a cluster of minimum 20 schools. The total common expense for 20 schools will be Rs. 1,00,000.

Mentor Cost : The mentor is the person in charge of visiting the schools on a daily basis and ensure compliance of the Sikshana program. Typically 20 schools are covered by a mentor and the total expense for such a person including salary, transportation and communication costs etc. will be Rs. 1,80,000 per year.

Unit Manager Cost : This block of 120 schools will be managed by an employee of Sikshana Foundation who will be responsible in ensuring compliance of Sikshana in all of the schools. The total expense for such a person including salary, transportation, communication costs etc. will be Rs. 3,00,000. The cost for managing 20 schools works out to Rs. 50,000.

Admin and Misc. Cost : This covers all the Administrative overheads in running the Sikshana Foundation. This includes salaries of the foundation staff, office running expenses etc. The cost to manage this block of 20 schools is estimated at Rs. 40,000.

Scholarships : This is an essential part of the Sikshana program which has proved itself to be a highly motivational initiative. The toppers from class 7 are awarded Rs.1200 per year for their 3 years of High School. In addition to the obvious benefit of the scholarship to the receiving student, the pyramid effect of increased competition for the same is the additional benefit. For 20 schools the estimate is that 50 children may qualify for the scholarship and the total allocation at Rs.1200 for 50 children for 3 years will be Rs. 1,80,000.

Contingencies : Over and above all the estimation a contingency amount of Rs. 10,000 has been provided in the project proposal.

# Text boxes

Mission & Objectives

To evolve a sustainable and replicable model for an effective and decentralized public education system based on good management practices

Location

Bangalore (Anekal Taluk)

Bi-annual progress reports will be generated on the entire cluster of schools. APF model testing will be resorted to in all schools in at least two levels twice—once at the start of the year and the other at the end.  These will be carried out by competent and independent agencies. Results will be announced as received from them. Un-audited financial results will be furnished during the middle of the year and the audited statements provided by end June of each year.