## Sheet1
Updated 19th Nov 2006
Expenses by categories | [9 empty] | INR
Expenses by categories
|  | in INR | %age of the total | [5 empty] | INR
| Conveyance/Travel/ refreshment | 2842 | 0.68485 | 2.77 % of the total |  |  |  | Funds raised from Asha chapter Arizona | 424900
| Stationery and Xerox | 140 | 0.033737 |  |  |  |  | Total expenses May 2006 to October 2006 | -414978.95
Note **** | Honorarium for services rendered+Refreshment | 8525 | 2.0543 |  |  |  |  | Balance will be added to Phase 3 | 9921.05
Note **** | Documentation expenses- individual families verified | 12032 | 2.8994 | 97.23% of the total
| Student welfare | 388143.95 | 93.5334
| Transportation of materials | 3296 | 0.79426
| Total expenses | 414978.95
Note- **** Higher documentation and honorarium charges have been incurred as compared to phase 1 because more paid social workers were required
for the individual family documentation. The project started nearly 1.5 years after the Tsunami
Items provided to children under back to School project for Phase 2
Item Nos
1 | School bag, drawing book, crayons/colours/paints (age appropriately) , lunch box
2 | Clothes as per requirement - two sets for children corporation, govt aided and govt schools and one set for private schools
Places | Type of request | How the requests have come | Total No. students | Boys | Girls | Classes | Previous supports of work Phase 1,2 | Remarks
Chennai 5 Nadukuppam Street1 | Area specific | Through UWF and social worker sathya | 55 | 24 | 31 | K to 12 | 12 students September 2005. This place was identified in phase I as one of the localities with empowered women who could move quickly to self reliance. Hence the support to the srea completely. Could verify individual families as the village was united under the headman who helped in intensive documentation | Completed July 2006
Chennai 5 Nadukuppam Street2 | Area specific | Through UWF and social worker sathya | 61 | 32 | 29 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street3 | Area specific | Through UWF and social worker sathya | 82 | 40 | 42 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street4 | Area specific | Through UWF and social worker sathya | 57 | 28 | 29 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street5 | Area specific | Through UWF and social worker sathya | 34 | 16 | 18 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street6 | Area specific | Through UWF and social worker sathya | 37 | 17 | 20 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street7 | Area specific | Through UWF and social worker sathya | 35 | 18 | 17 | K to 12 |  | Completed July 2006
Chennai 5 Nadukuppam Street8 | Area specific | Through UWF and social worker sathya | 32 | 15 | 17 | K to 12 |  | Completed July 2006
Nochinagar Chennai4 | Area specific | UWF | 11 | 0 | 11 | Std 2 to11 | 10 students completed in Oct 2005 | Completed July 2006
CPS Tiruvanmiyur Kuppam | School | Through headmistress, she has requested three NGOs for all the children. We have agreed to take up 100 as the funds are sufficient for this | 100 | 50 | 50 | Std 1 to 5 | Taken up now in Aug 2006 | Completed Sept.2006
St.Paul's Public School Nalla thaneer Odaikuppam-Toll gate | Area specific | Through UWF and social worker Ramani | 38 | 27 | 11 |  | to be taken up end Aug 2006 | Completed Oct 2006
|  | Totals Phase 2 | 542 | 267 | 275