Eureka Makkal Noolagam

Eureka People’s Library

Introduction

The need for a village library need not be explained.  The Government has started a number of libraries with building and fulltime staff – but the quality of selection and the overall approach ensures that the library caters only to young well educated men.  Neither children, nor women nor adolescent girls ever enter the library to read books.

There is a strong need for a women and children centered library movement in the country.  In places where individuals have started such libraries it has proved quite successful.  All such efforts have attempted to take books to people’s homes instead of bring people to a central library to read the books.  A motivated young person from the village with a few good quality books, but who takes books to people and helps them read can create a much better library reading culture than a lot of books rotting in a dusty scary building.

How to scale up such library attempts?  How to make a low cost library movement feasible?  How to generate books for such libraries?   These are the questions the Eureka People’s Library Movement tries to answer.

We have experience in continuously producing low cost good quality materials.  We have experience in running a number of small libraries.  We also have experience in running large field programs with village volunteers and cluster coordinators. Finally we have a lot of experience in working with a large number of NGOs and people’s movements and in bringing them together, training their activists and getting a common program started.

This library movement will require all of the above skills – and possibly more!

The Proposed Goal:

1. To start 5000 village libraries all over Tamilnadu that are actively supplied with reading materials and that provide regular feedback on usage of the materials.

2. To use these libraries to promote good quality progressive and educative reading materials for children, adolescent girls and boys and older neo-literate women in the villages.  The materials will include story cards, books, health and education booklets, and other progressive reading materials.

3. To use these libraries to launch a larger production capacity for low cost, high quality materials so that a wide section will not only read it, but will be willing to also buy it. Therefore beyond the 5000 libraries the materials can be purchased by government schools, other NGOs, institutions and individuals – the initial print run ensures that the cost is low enough for many more people to buy the materials.  
Approach

Imagine a village library – with a small room on rent (Rs.200/month), a local paid library coordinator (Rs.500/month) and 400 books (Rs.8000).   The annual cost for such a library comes to Rs. 16400.  With some coordination expenses, shelves for the library, etc, this will come to Rs. 20000/library.  The cost for 5000 libraries comes to Rs. 10,00,00,000 – 10 Crores for 5000 libraries!  A really huge cost.

If we decide to scale down the library to merely 500 libraries, then the cost comes to Rs.1,00,00,000  - 1 Crore.  Even this is a huge cost.  But even if the money were available, the problem now is getting the 400 books.  Unfortunately today you cannot get 400 good books in Tamil for children and neo-literates.  If we decide to print it, with a print run of 500 copies the cost per book goes up significantly.

With half the above cost (that is with Rs. 50 Lakhs), we can plan out 5000 libraries if we restructure it. This is what the current proposal aims to do.

Library Structure

As the diagram shows, the state center produces materials and distributes coordinates, gets reports, etc for the 5000 libraries – this is done at Chennai by AID-INDIA.  For every 500 libraries we have an AID Library Network Center – an office with one fulltime person coordinating it.  This Network Center contacts 10 NGOs (or fewer) and get each NGO to start 50 libraries (or more) in villages and schools.


Material Supply

Each Village library is given a well designed library bag with flaps for story cards, 20 small low cost books, 20 costlier books, register and membership cards.  An unpaid village volunteer runs the library.  She is given the bag with an initial set of 16 laminated 1 page story cards, 20 small low cost books and 20 costlier books. She is also given a register and a set of color coded membership cards.

She registers all the members on the first few pages of her register and issues them a membership card.  She charges each member Rs.5 one-time and gives this money to the network center through cluster center. She then loans them the books (and notes it in the register serially and also on their card).  When a person returns the book, she ticks off their name on the register.  Keeping the register entry and book-keeping simple is the key to success.  

Every month she is given a new set of 8 laminated color story cards and some additional booklets and concept booklets and health materials – that add to the library.

Coordination
How to supply the village volunteer with the materials regularly and get reports on usage?  This is where the coordination structure comes in.  Each cluster center has a library coordinator (a fulltime person devoted to this program – who either works alone or with others in the NGO).  The coordinator gives the new set of 8 story cards and additional booklets to each village library coordinator and notes down two numbers from her register – number of people who are currently members and the number of books loaned out this month.   This information collected over 50 libraries forms the basic report from the Cluster coordinator.

All the 10 cluster coordinators meet together with the network coordinator at the network center once every month.  The Network Coordinator (an AID-INDIA Full-timer) collects the reports from the cluster coordinators and gives them the next set of story cards and books.  The network coordinator also uses this meeting to provide them with training on how to use the library in more creative ways – puppet shows, magic shows, experiments, discussions sessions, dramatizing stories, organizing children’s melas, poster exhibitions, etc.

The 10 network coordinators meet together with the state coordinator every month where they give in their reports and collect the next month’s materials.

In addition, the state coordinator and the network coordinators visit each NGO regularly and help them on the field.  The network coordinators must visit each NGO library centers once every month at least.  At the review meetings, apart from the data reports, qualitative reports on experiences must be included on the events at different libraries.  The Cluster coordinators will apart from helping the libraries also organize programs in the libraries for children and will also sell science concept booklets and books that we produce to schools if possible.

Training

Every month the network and cluster coordinators will be trained on activities that can be done in the libraries.  In addition to this, every six months, all the network coordinators will have a 3 day training workshop where they are trained in a number of mobilization activities, street plays, youth projects, science experiments, metric mela, video discussions, etc.  Apart from this, in each cluster by rotation, we can organize special training camps for the village volunteers.  In interested clusters, the network coordinators will organize local kalajatha teams, sports clubs or youth project seminars. These activities are possibilities within the library that can be budgeted separately.  In many of the clusters, we can provide a set of video CDs with a VCD player and have a series of video discussion programs.

Exchange

Instead of providing all the villages with exactly the same set of books, we will be providing different books to each village so that they can be exchanged.  The details are below:

1. The library cards and 20 Eureka books (the low cost ones that we produce) will be common – the same ones provided to all the libraries – no need to exchange. Same with the monthly cards and small booklets and pamphlets. This is because all these are very low cost. 

2. Apart from these we will provide 20 ‘outside’ books to each library.  These books will have to be exchanged every 6 months. To make things simpler at the cluster coordinator and village library level, all the villages in each cluster are given the same set of 20 ‘outside’ books.  But each cluster is given a different set of 20 outside books.  This means at a network center we have 10 different 20-book sets.  Call them Set 1, Set 2 … Set 10.  The network center has 50 copies of each set.  At the beginning the network coordinator gives 50 copies of Set 1 to Cluster 1, Set 2 to Cluster 2, etc.  Six months later, all the cluster coordinators collect these books back and give it to the network coordinator.  The network coordinator exchanges them and gives Set 1 to Cluster 2, Set 2 to Cluster 3 … Set 10 to Cluster 1.  This ensures a new set of 20 costlier books to each village every 6 months – for at least (60 months) 5 years. 

In all this means we need to buy 50 copies each of 200 different good books for each network center.  If we decide to exchange between network centers, then we need to buy 50 copies each of 2000 different books. There are two problems with this. There aren’t 2000 different good books in Tamil for children and neo-literates!  Secondly, buying 50 copies of each book does not make our bargaining position very strong.  Therefore inter-network exchange is not a viable option and we will restrict ourselves to intra-network exchanges only.

This means we need to buy 500 copies of 200 different books in all for the 5000 libraries.

Library Usage Data and Reports

Every month we will get reports of how many members and how much book transaction happens in each village library.  This information can be compiled into a state wide report and put up on the web and can be made available. But this does not tell us how many people have read how many books.  Nor does it tell us information about how popular each book is.  For the former, we can use the membership card to get an overall picture.  The membership cards are color coded – yellow card is the starting card, once a person has completed the yellow card (20 books) he/she returns it and gets a blue card. Once the blue card is completed, he/she returns it and gets a green card and finally a red card.  Based on the number of cards of each category given out and collected back, we can find out how many books each person has read.  But even this does not give us enough information on the popularity of each book.  To do this one would need to have a separate dip-stick or sample study undertaken in different clusters.  Such a study is not a part of this proposal, but can be done separately after a year by a different team (maybe by a team of interns or volunteers) who can look at different categories of books and suggest ideas on how we should structure the library material production in the future. One can at that stage also plan an independent external evaluation of the program.

Human Resources and Practical Implementation

If one is planning a 5000 library network that is completely independent of all other efforts, the costs will be significantly higher.  We have assumed that one cluster coordinator can easily start and coordinate 50 libraries.  This assumption uses the fact that the cluster coordinator is part of an NGO that has a lot of local programs and that is interested in adding a library program to their activities.  Let us therefore look at the practical field realties that can make or break this program.

Let’s say we have identified good, honest and decent NGOs.  This requires a lot of work – but since we have been working in Tamilnadu for several years, we know many of the good groups already.  Within this set of good organizations, there are 4 categories:

1. Category A Organizations: That are looking for such a library opportunity already and are capable of raising sufficient funds themselves.  These maybe organizations that are running SHGs or an NFE program and want to add a library as part of the programs. We can ask these organizations to assign a fulltime coordinator for this program and also ask them to pay a part of the costs for the library materials.  The coordinator will attend all our meetings and submit reports and feedback, etc.

2. Category B Organizations: Running a library is part of the organization’s agenda but they cannot pay for the library materials.  They have enough money to pay for a coordinator and assign him/her to this program fulltime.  There is no money given out or received – only materials. The coordinator works within the organization and attends monthly meetings at the network center and gives us reports, etc.

3. Category C Organizations:  These organizations don’t necessarily have library as a main agenda and/or do not have funds/ability to pay a fulltime coordinator for the library.  We not only give them the library materials, but also pay for a fulltime cluster coordinator to run the library.  Of course the coordinator will attend the monthly meetings and submit reports, etc.

4. Category D Organizations:  These organizations want a library, don’t have money for a fulltime coordinator, but don’t want us to pay for a fulltime coordinator either.  They may therefore not be able assign a fulltime person to follow up, give us feedback, reports etc.  But they may be good people’s movements that are able to utilize the library materials very effectively.  We maybe able to organize two things with these organizations:

a. They pay the full or a subsidized price for the library and utilize the library program.  If they pay the full price, we don’t ask them for reports. If they pay a subsidized price, we ask them for reports.

b. They don’t pay (or pay a very nominal amount) for the library materials, and have an unpaid volunteer coordinator assigned to report the progress and to attend the meetings etc.

       At any rate, our network and state coordinators must be able to visit these groups and   

       get a feedback on the libraries periodically. 

Our estimate is that we will find a lot of organization in Category C, a few in Category A and B. Category D organizations like TNSF, PSF, MALAR, Construction Worker’s Union, etc have already been identified and they can themselves utilize all the 5000 libraries, but we will start with these only after we have a significant number of libraries with other categories (where we can ensure sufficient regularity of reporting).

More practical issues

1. We said earlier that the cluster coordinator gives the library materials to each village library coordinator.  Actually she may just distribute the library materials to the SHG coordinators during their monthly meetings and ask them to start the libraries in their areas.  Often this may mean that one library coordinator can start and coordinate 100 libraries.

2. In Category A and B – the NGO clearly has to arrange funds from other sources.  Even in Category C where we fund the coordinator, the NGO has other office expenses to cover.  Most of the NGOs are looking out for good projects that funding agencies would be willing to support. This library program would be something the NGO can present to other funding agencies – either as part of their SHG/NFE programs or as an independent program – and get funds from them.  We should not only not prevent NGOs from doing this, we should actively encourage the NGO to do this. In case they get such funding for it, we can shift them into Category A – reducing the financial burden on us.  Over a longer period of time, we should shift into a mode where we merely supply material, provide training and coordination, and each NGO is responsible for raising their own funds for paying for the library materials and coordinator’s costs.

3. The amount paid to the cluster coordinators may not be sufficient.  Also given the fact that the cluster coordinators are visiting so many schools and villages and meeting school children, they are in a good position to sell many of our Eureka Concept Booklets. These booklets priced at Rs. 2 and Rs. 3 – can be sold to school children or teachers.  We offer these booklets each month to the cluster coordinators and ask them to sell them.  For the sales they make, we give them a commission of 25%.  This helps them earn some money and helps us reach our materials to more children.  In some movements, this commission can be kept with the local movement or the NGO – if they so decide.

4. For most NGOs we will have to stick to 50 libraries per coordinator.  But more evolved organizations with a good structure can manage quite well with 100 libraries per coordinator.  This will bring our coordination costs down.  Also instead of a network center for 500 libraries, one can plan a network center for 1000 libraries.  This again depends on the network coordinator’s abilities and also the NGOs he/she is in contact with and how easily they can add on a library program.

5. Where ever we are already supporting an NGO for a health or a primary education program or a pre-primary education program or a science education program, we will automatically add a library component to the program under Category B – unless the NGO is capable of paying for the library from other funds in which case it can be graduated to Category A.

6. If government schools are willing to pay for the library materials and buy it, we can start the libraries in several schools as well.  We can even approach local Rotary or Lions Clubs to sponsor the libraries for the local government schools.

All of this means that we do not have a fixed strategy with every group.  This is essential because there are different kinds of groups across the state and a single strategy is not the best way for all groups. Our state and network coordinators will have to internalize the purpose of these varying strategies and our overall goal of reaching the poorest of the poor in each village with materials that will bring them together and provide them with education about the world around them.  Once this internalization of the basic ideas has been achieved, they will have to assess the capacity and category of each group and work out a strategy with them.  Only this can ensure an effective program and at the same time reduce our financial burden for this program.   We will have to budget this program assuming the worst case situation – all groups in Category C, with 50 libraries and all network centers with 500 libraries.  If we are able to get many groups in Categories A and B and are able to start network centers with 1000 libraries, we can utilize the extra funds saved on coordination expenses on printing additional books instead or we can use it to expand the program to more libraries clusters – maybe in Category D.

Once the basic library backbone is structured well, we can think of working with these library clusters by adding a video library or a slide library or a toy library or a larger book bank system to the program. One can also think of a newspaper for these libraries. We can train the coordinators on adolescent girl health classes and youth projects and organize these in each library. Sensitization materials and training on caste, gender, inequality, poverty, etc can also be provided and used in the libraries. All these programs can be planned at the second stage.

Budget for One Year

Unit Cost for 500 Libraries

1 Network Center with 10 Clusters of 50 libraries each

	Particulars
	Rate (Rs)
	Number
	Cost in Rs

	Material Costs
	
	
	

	Library Bag
	100
	500
	50000

	2 Color Laminated Story Cards
	2
	500 x 112
	112000

	40 Eureka Books over a year
	5
	500 x 40
	100000

	20 Outside Books once in 6 months/library
	15
	50 x 20 x 10
	150000

	Library Register and 50 Membership Cards
	30
	500
	15000

	Material Transportation Costs
	
	
	15000

	Material Cost Subtotal
	
	
	442000

	

	Coordination Costs
	
	
	

	1 Network Coordinator Salary
	2000
	12 months
	24000

	10 Cluster Coordinators Salaries
	1000
	12 m x 10 
	120000

	Travel Allowance for all 10 people
	400/month
	12m x 10per
	48000

	Travel Allowance for network coordinator
	800
	12 months
	9600

	Network Center Rent and Utilities
	1500
	12
	18000

	Monthly Review Camps at Network Center
	80/person
	15per x 12m
	14400

	Special Training Camps at Network Center
	5000
	2
	10000

	Documentation and Communication
	1000
	12
	12000

	Coordination Costs Subtotal
	
	
	256000

	

	Total Costs for One Network Center

with 500 Village Libraries
	
	
	6,98,000

($ 15,500)


State Coordination Expenses

	Particulars
	Rate (Rs)
	Number
	Cost in Rs

	State Project Coordinator
	5000
	12 months
	60000

	State Material Production Coordinator
	5000
	12 months
	60000

	Travel for State Coordinators
	1000
	2 per x 12 m
	24000

	Material Production/Design Costs 

(Hon, camps, DTP, layout, cartoons, etc)
	
	
	100000

	Monthly State Review Camps
	100
	15per x 12m
	18000

	State Training Camps (2 days – 2 times a year)
	150 x 2
	100 per x 2
	60000

	Documentation & Communication
	2500
	12
	30000

	Total State Coordination Expenses
	
	
	3,52,000

($ 7800)


The Total Network Level Budget for 5000 Libraries is 69,80,000 ( Rupees 69 Lakhs, 80 Thousand). This works out to about US $ 1,55,000.  

With State Coordination Expenses the total cost for 5000 libraries =Rs.73,32,000. 

The annual per library cost = Rs.1466 – less than Rs. 1500 ($30) per library/year!

Each organization/chapter can support the cost of one network of 500 libraries.

Steps and Timeline for Basic Activities

	No
	Activity
	Time Line
	Responsibility

	Activities Already Completed

	1
	Identify State Project Coord – Vijay Anand
	Done
	

	2
	Identify of Material Coord– Viji
	Done
	

	3
	Prepare proposal and project note
	Done
	

	Activities In APRIL

	4
	Arrange funds for the project
	By April End
	Chandra/Balaji

	5
	Prep/print set of 60 Laminated Story Cards
	By April End
	Viji

	6
	Prep/print set of 20 Eureka  story books
	By April End
	Viji/Balaji

	7
	Design, train, produce 1000 library bags w logo
	By April End
	Malini

	8
	Identify, bargain and buy 200 outside books (100 sets)
	By April End
	Vijay Anand, Chandra

	9
	Design/print register and membership cards w logo
	By April End
	Vijay Anand/Chandra

	10
	Contact NGOs and prepare NGO list with numbers
	By April End
	Vijay Anand

	11
	Identify 2 Network Centers and Hire Network Coords
	By April End
	Vijay Anand

	12
	Negotiate with each NGO regarding funds & materials and finalize cluster coordinators – for 2 networks
	By April End
	Vijay Anand w/help of Prabha, Chandra, Balaji

	Activities in MAY

	13
	First NGO Cluster Coordinators Meeting to kick start library with 2 network centers – 1000 libraries
	May 1st week
	Vijay Anand and Viji

	14
	Supply of Library materials to each network center and cluster center
	May 1st week
	Vijay Anand and Lokesh

	15
	A round of Cluster Visits to help start the libraries
	May
	Vijay Anand, Banu

and Network Coords

	16
	Continue Production of Bags
	
	Malini

	17
	Continue Producing Lib Story Cards and books
	
	Viji

	18
	Continue identification of new NGOs and 

new network cords and centers
	
	Vijay Anand

	Activities in JUNE

	19
	First monthly meeting at the 2 network centers
	June 1st week
	Vijay Anand and Network Coords

	20
	Complete list of NGOs in other 8 network centers. Finalize funds and cluster coords
	By June end
	Vijay Anand w/help of Prabha, Chandra

	21
	Second NGO Cluster Coord meeting to kick off  the lib in the remaining 8 network centers
	By June end
	Vijay Anand and Viji

	22
	Complete rest of 4000 bags
	By June End
	Malini

	23
	Buy the next 400 copies of the 200 outside books
	By June End
	Vijay Anand, Chandra

	24
	Identify 8 more Network Centers and Coords
	By June End
	Vijay Anand

	Activities in JULY

	25
	Second Monthly meeting at the 2 network centers
	July 1st week
	Network Coords

	26
	Supply lib materials to all network centers and cluster center 
	July 1st week
	Vijay Anand, Lokesh

	27
	Cluster visits to all the clusters
	July
	Vijay Anand, Banu

	28
	First State Level Monthly Network Coord Meeting
	July 2nd week
	Vijay Anand

	29
	State level program guidance committee 

to review progress made
	July 4th week
	Balaji, Chandra, 

Vijay Anand, Viji

	Activities in AUGUST

	30
	Monthly meetings at the 10 network centers
	Aug 1st week
	Vijay Anand

	31
	Second State Level Monthly Network Coord Meeting
	Aug 2nd week
	Vijay Anand

	32
	Negotiations with TNSF, MALAR, PSF, R.Gita, 

and others on starting Category D Libraries
	Aug 4th week
	Balaji, Vijay Anand, Chandra

	Regular Activities Continue throughout August and from September Onwards

	Special Activities from October onwards

	33
	1st Quarterly Review meeting with all cluster coords
	October 2005
	Chandra

	34
	If negotiated, start of Category D Libraries
	October/November
	Vijay Anand

	35
	Half Yearly Collection/Exchange of Books
	December 2005
	Vijay Anand

	36
	2nd State Training Camp
	December 2005
	Vijay Anand

	37
	Special Training Camps if everything goes smoothly
	Dec 05/Jan 06
	Vijay Anand, Viji

	38
	3rd Quarterly Review Meeting with all Cluster Coord
	February 2006
	Chandra

	39
	Annual Review meeting with State Training Camp
	May 2006
	Vijay Anand

	Regular Activities Continued After First Initiation 

	1
	Monthly Production of Booklets, Story Cards
	End of each month
	Viji and Vijay Anand

	2
	Monthly Supply of materials to network center
	1st week of month
	Vijay Anand, Lokesh

	3
	Monthly cluster coord review meetings
	1st week of month
	Network Coord

	4
	Monthly network coord meetings at state level
	2nd week of month
	Vijay Anand

	5
	Report finalization and emailed to donors
	4th week of month
	Vijay Anand, Balaji


PAC: A program action committee consisting of the following can be formed immediately to meet monthly and guide the day to day working of the program:  Vijay Anand, Viji, Chandra, Ravishankar, Balaji, Smitha, Prabha, Damu, Lokesh, Banu and Samu.  Others can join this committee if they would like to spend time thinking about the program and helping expand the network.  This committee should every month, look at the progress and also approve the daily finances for the project. The overall finances will be coordinated by the AID Admin Committee.

PGC: A program guidance committee consisting of the following can be formed to set the overall direction of the program and should meet every quarter to review the progress of the program.  Apart from the PAC members, it will have Dr. Vasanthi Devi, CEK, Ramanujam, Madasamy, Franco, Rajan, Ram, Aruna, Bhooma Parathasarathy and Vibha.

A Eureka Children’s Library in Every School

A good children’s library requires not a concrete building and lots of shelves.  It requires good quality child sensitive materials that children find easy and attractive to read.  It requires an affectionate person who gives the child this material and encourages the child to read.  It requires regular reading activities that celebrate the child’s reading skills.  It requires a ‘newness’ to the library every month.

With the child as a focus we have developed a Children’s Library Program meant for children in Government and Corporation Primary schools.  

Each library is given an attractively designed library bag with a flap for story cards, a flap for 20 small books, a flap for 20 bigger books, space for a register and for membership cards.

The library bag comes with an initial kit of:

1. 16 Story Cards:  These are laminated 1 page (2 side) colorful story cards with attractive cartoons. The stories are designed such that even the new learner can find the reading easy and encouraging.  Sentences have only 4-5 words each and the story can be read in 15 minutes by a neo-literate reader.  The stories are designed to be fun and interesting for children.  Many of the stories can be acted out in the class by the children themselves.

2. 20 Small Eureka Books: These are 16 page story books that are again colorfully designed and easy to read. A book will typically take a child half an hour to read.

3. 20 Bigger Books:  These are a selection of good children’s book made from the existing published literature of children’s books in Tamil.  Ideally different books can be purchased and provided to different schools and they can be exchanged.

4. 5 Science Concept Booklets: These are 16 page booklets that explain a primary science topic using cartoons and pictures and can be used by the teachers to explain the topic to children.

Monthly Additional Materials for the Library:

Every month the school library is supplied with a new set of 8 story cards, 1 science concept booklet (5 copies) and 1 Eureka story book (5 copies). This apart from building an excitement in the library also encourages children to complete the older books and story cards and await the newer ones.  If the school has a facility for Video CD screening (a VCD player and a TV), the library can be additionally supplied with one video CD each month.  Depending on the school’s need, the number of copies of the above materials can be changed.

Supply Chain:

To keep the supply costs minimal, AID-INDIA will supply the materials to one or two centers specified by the Corporation’s Education Department. The department can supply it to the schools through the HMs or the Teachers during their regularly monthly meetings or training sessions.  This will cut down the cost of monthly transportation.

Training:

To make the library program an effective one, each school much assign one teacher as the library coordinator. She/he can organize the library in the school, attend the trainings and collect information on the library usage and provide it to the Corporation’s Education Department.  At the beginning of the year, while providing the library bags and kits, AID-INDIA’s resource persons can train these teachers on usage of the library materials, on how to get children to maintain the library themselves and on how to get children enact the stories, and do activities around the library.

Costing

Each Library will involve the following costs (assuming we have 400 libraries in Chennai): 

Initial Cost

Library Bag 




= Rs.  100

Library Register and Membership Cards
= Rs.
40

16 Story Cards



= Rs.
32

20 Small Eureka Story Books


= Rs.   80

20 Bigger Books



= Rs. 160

5 Science Concept Booklets


= Rs.   15

Total Initial Cost



= Rs.  427

Monthly Library Cost

8 Story Cards




= Rs.
16

1 Science Booklet (5 copies)


= Rs.
15

1 Eureka Story book (5 copies)

= Rs.
20

Total Monthly Cost



= Rs.   51

Annual (Initial + 9 months) Cost for the Library for Each School = Rs. 886

For 400 Libraries the total cost of the program for one year = Rs. 3,54,400

From: Pamela Ribon

Sanjeev,

I know it is early in the rebuilding process, but I'm hoping I can be

of some assistance.  Every year my website runs a book drive for public libraries who have lost their funding and desperately need new books for their collections.  This year I'd like to focus the attention on the Tsunami relief, specifically on the rebuilding of schools that have been destroyed.  We  can do this monetarily, but usually we find a way to have Amazon.com ship books to the schools in need by having the school set up a wishlist through the site.

Seeing as how we are now dealing with an international crisis, I'm

wondering how I can help send books to a school.  Is it still better to send a monetary donation?  Is there a place where we could order books to be sent?  Do you have a supplier where we could send our

contributions?  We tend to do this fundraiser every May, so this does leave a few months to work together, so I can get the publicity needed to send, hopefully, thousands of books to the rebuilt schools.  I know that supplies are needed as well as uniforms, backpacks -- whatever it takes to rebuild the schools.  We can focus on one needy school in particular, or an entire city.  We just want to help, and since I'm in Los Angeles, I have no idea where to start.

I'm asking you because I saw your name on the Asha for Education

website. I hope this finds you healthy and safe, and I hope I can help.

Thank you.

Pamela Ribon





















50 Village Libraries per Cluster





50 Village Libraries per Cluster





10 Clusters





50 Village Libraries per Cluster





50 Village Libraries per Cluster





State Center Material Production





500 Lib Network Center





500 Lib Network Center








10 Clusters





500 Lib Network Center








500 Lib Network Center








10 Clusters





10 Clusters








