**Sept 16 2021**

**Attendees - Ranjita Radhakrishna (from Asha), Meril**

Covid tests have reduced and so cases aren’t being recorded.

50% of the people are taking vaccinations. Religious people aren’t still accepting.

Regarding Belaku:

- 12 children are there currently.

- 6th to 12th school has started as per govt. Order to commence 1st to 6th standard classes yet pending from govt and expected in October 2021.

- From Oct 1st, Belaku will start full fledged.

* Totally, 25 children will be there in Belaku.
* 2 new charges need to be included in the budget and this shall be done by Meril Sir when he shares the new budget sheet:
	+ Gas Cylinder and firewood - 16,500 INR
	+ Auto charges - 24,000 INR
* Change to budget sheet which will be done by Meril Sir: Food for children will be included and no kits will be provided as children will come to school.

Budget sheet will be split into 2 sections:

 1. July, Aug, Sep 2021 —> 12 children were supported.

 2. Oct 2021 to March 2022 —> 25 children will be supported.

Regarding PPC:

* 35 children will be enrolled.
* During July, Aug and Sep 2021 few children were coming and so other repairs like shed, floor upgrades have been done.

**Sep 23 2021**

Budget sheet shared with Revathi, Niti and Ravi was discussed. Wiki page to be created for voting and sent to Asha Chicago chapter.

Checklist for next disbursement needs to be submitted by Oct 10th.

Review old budget sheet to confirm that the budget is close to previous years.