APPLICATION FOR FINANCIAL ASSISTANCE FROM 
PEOPLE’S ACTION FOR TRANSFORMATION (PAT) 
FOR CHILDREN DEVELOPMENT PROGRAMME BENEFITING 
50 CHILDREN THROUGH DAY CARE CENTRES 
IN THE SLUMS OF TRICHY, TAMILNADU, INDIA

(Motto : Children - our Hope for a better tomorrow)

Title of the Project	:	CHILDREN DEVELOPMENT PROGRAMME

Name and Address	:	K. Hirudayasami
	of the Applicant		President
			77/2, 5th Cross, Arunachala Nagar, Crawford, 
                                                             Trichy-620012.  : 0091- 431 – 2471717
		   Cell : 0091- 94437 - 53766

Legal holder of the	:	People’s Action for Transformation (PAT)
	Project		No. 4, A-Block, St. Paul’s Complex, Bharathiar Salai,
                                                             Trichy – 620001.
			 : 	0091 - 431 - 2413434

Name and Address	:	R. Stephen
	of the Primary contact		Programme Coordinator
			Plot No. 4, Kailash Nagar,
			Poovalur Road, Lalgudi Po. & Tk.
			 : 0091- 431 – 2544807
			Cell : 0091 - 94439 - 04631

Legal Status of the 	:	Registered under the Indian Trust Act
	Organization		Reg. No.107/97

Registered under Foreign Contribution Regulation
			Act with the Ministry of Home Affairs, 
			Government of India	
			Regd. No. 076040280 dt. 28.09.2001

Place : Trichy -1.

Date  :  27.09.2006

PROJECT PROPOSAL

I	INTRODUCTION

We would like to begin the proposal expressing our genuine gratitude for what you/Asha for Education, Stanford & Canada had been and are to the children of our slums. The timely intervention by way of your contribution towards the programme and construction has rescued us from an awkward and inconvenient situation. Your prompt act in the first instance, had ensured the continuity of CDP thus making us heave a sigh of relief. Secondly, it eased the burden of the dear Rotarians who had otherwise to incur the total expenditure of the project. Thirdly, it had created a close bond between Asha and PAT for a sustained educational betterment of the slum children.

As a result, Asha has become a pet name in the neighbourhood of the project location. All the parents are aware of Asha as the funding source of the project which not only takes care of their children but also enables them go ahead with their daily tasks without undue anxiety.

Such is the cherishable situation prevailing at present in the project site.

# II	OUTCOME OF CHILDREN DEVELOPMENT PROGRAMME

Due to our personal involvement among the slum dwellers right from 1999 till date thanks to CDP, we could perceive the following changes :

On the  social front :

i	There is a gradual increasing cooperation on  the part of the parents with PAT for the smooth running of this programme.

ii	Their attitudinal change is evident in forcing their children to pursue education rather than allowing them to accompany them to their hazardous worksite.

iii	The weekly house visit made and the monthly parents’ meet conducted by the teachers have produced the desired result among the parents to send the children neat and clean to the centres daily.

iv	Atleast on the part of the children we could see the abstinence from using indecent and vulgar words.

v	The parents are becoming sensible enough to refrain from heaping undue demands on us.

vi	The reconstruction of the centres has surely enkindled their spirit and Asha’s splendid effort has come for a notable appreciation.

vii	The continued role played by the Rotary fraternizes the inhabitants around CDP centres.

On the economic front:

i	We could observe a very insignificant level of advancement among the target parents except that they are enabled to take up their daily work without remaining at home to look after the children.

ii	They start realizing that their children are not as unfortunate as they had been on the ground that through this project their children are nourished with noon meal and given a cup of nutritious drink in the evening; they are distributed with 2 sets of uniform; they are given a good grounding on education through play-way methods. And above all they are nursed with love, affection and medicine.

III.	NEED FOR THE CONTINUITY OF CDP

In the light of whatever has been discussed above and considering the time still required for the parents to liberate themselves from their ignorance and making them give due importance towards upbringing of their children, we feel the indispensability of the project. Moreover, we feel it strongly that our move in the direction of running Day Care centres among the slum children should be extended further to the adjacent slums so that a tangible and a collective transformation could be witnessed.

IV.	THE OVERALL OBJECTIVES OF THIS PROJECT INCLUDE :

	To feed Children with nutritious diet and drink.

	To pay medical attention to their ailments.

	To provide clean clothing

	To create stimulative play environment & basic awareness

	To encourage more co-operative learning

	To create opportunities for children to learn by doing

	To develop low cost materials for them to acquire first hand experience

	To foster independence and creativity by encouraging self expression

	To develop children’s ability to communicate effectively.

	To ensure that the activities in the centres are related to their own world.

V.	 SPECIFIC OBJECTIVE OF CHILDREN DEVELOPMENT PROGRAMME (2-5years)

The selected 50 children aged between 2-5 years from 2 slums would become nourished with nutritious diet, reared in good self habits and in relating to others, provided with learning opportunities, medical care and uniforms. They would become ensured of physical and psychological safety and their overall development would reach 90% at the end of one year.

VI.	SUGGESTED METHODOLOGIES

As to “How” we intend to realize this objective, we shall continue the following methodologies which are in existence.

1.	Running Day - care centres.

2.	Serving Nutritious diet.

3.	Providing Medical Check-up and treatment

4.	Providing Uniform

5.	Promoting interaction with parents

6.	Initiating children into activity oriented learning.

## VII	PROGRAMME BUDGET

S.No.	Nature of expenses	Amount

1	Facilitation support by PAT staff 
		Honorarium for

a) 1 Programme Coordinator @ Rs. 3150/- 
		    per month for 12 months

1 No. x Rs. 3150/- x 12 months	37800

b) 2 Child Development teachers @ Rs. 1050/- 
		   per month per staff for 12 months

2 Nos. x Rs. 1100/- x 12 months	26400

c) 2 Assistants @ Rs.800/- per month per 
		   person for 12 months

2 Nos. x Rs. 800/- x 12 months	19200

2	Training the staff (Refresher training)
		5 persons x 4 days x Rs. 75/-	1500

Honorarium for Resource person
	1 No. x 4 days x Rs. 500/-	2000

3	Rent @ Rs. 300/- per centre for 2 centres
	for 12 months.	7200

4	Supply of 2 sets of uniforms @ Rs. 175/- 
	per set for 50 children per year.	17500

Supply of 2 sets of uniforms for teachers and assistants
5 Nos. x 2 sets x Rs.300/-	3000

5	Utensils, Plates, Tumblers, Buckets, Steel box 
		and minimum furnitures @ Rs. 5000/-per 
		centre for 2 centres (1 time)	-

6	Supply of provisions and groceries @
		Rs.7670 per month for 11 months for 2 centres	84370

7	Supply of educational aids @ Rs. 3000/-
		per centre for 2 centres	6000

8	Medicine @ Rs.100/- per child per year for 
		50 children including referral.	5000

9	Printing, Stationary, Postage & Documentation	4000

10	Miscellaneous 	5000

Total	218970

In US $ @ Rs. 46/- (INR)	4760

VIII	 MONITORING & REPORTING

The Programme Coordinator will have overall control of the daily functioning of the centres with the total assistance from the supervisor and will conduct the review meeting on every Saturday. Monthly Statement of Accounts will be maintained. Half yearly report and Annual Report will be submitted to the Funding Agency with full details on project and accounts.

IX	 CONCLUSION

We firmly believe that the programme of this sort is a compulsory input in the strategy of human resource development. It is a feeder and support programme for primary education, and also a support service for daily wage earning women of the disadvantaged sections of the community. If we are given the support, we would bring about not only the desired development in children but also would ensure the involvement of the respective parents who would become prepared to extend care, affection and early childhood education to their children. Thus we will be proud of nurturing better citizens for our country.

ACTION PLAN (Project Description) (ANNEXURE 1)

Sl	Nature of the	1	2	3	4	5	6	7	8	9	10	11	12	No. of	Who	Means of
No.	Activity														Activities	Discharges	Verification

1.	Training the Staff	x			x			x					x		4	Resource	Training	
(Residential)															persons	materials,																		Reports, Photos

2.	Identifying &	x													1	Child 	Survey Records			enrolling children															Development		
		of 2-5 years															Staff

3.	Admitting children in	x													1	Child 	Admission			Child Development															Development	form		
		Centres															Staff

4.	Maintaining	x	x	x	x	x	x	x	x	x	x	x	x	12	Child  	Attendence  
		Attendence Register															Development	Register																			Staff	CDS Report

5.	Supply of uniform to															Programme
		children & staff	x													1	Coordinator

6.	Distributing	x	x	x	x	x	x	x	x	x	x	x	x	12	Supervisor	Gross Stock			provisions 															Child	Receipt				& groceries towards															Development Staff	& Issue Register			Nutritious diet

7.	Maintaining Stock	x	x	x	x	x	x	x	x	x	x	x	x	12	Supervisor, Child	Stock Receipt &
		Register of Centres															Development staff	Issue Register

8.	Feeding the children	x	x	x	x	x	x	x	x	x	x	x	x	12	Assistants	Stock Receipt &
		with noon meal and																Issue Register			nutritious drink in
		the evening

9.	Manufacturing &	x	x	x	x	x	x	x	x	x	x	x	x	12	Programme 	Inventory				Providing Play															Coordinator	Register				Articles																Teachers &																			Assistants

10.	Implementing	x	x	x	x	x	x	x	x	x	x	x	x	12	Child 	Syllabus Note, 
		Syllabus															Development Staff	Performance																			papers

11.	In-service Training 	x	x	x	x	x	x	x	x	x	x	x	x	12	Supervisor 	Minutes Book

12.	Conducting Review 	x	x	x	x	x	x	x	x	x	x	x	x	12	Programme 	Minutes Book			Meeting for staff															Coordinator

13.	Weighing Children	x	x	x	x	x	x	x	x	x	x	x	x	12	Child 	Growth
		Periodically															Development	Monitoring																		staff	Register

14.	Providing Medicare	x	x	x	x	x	x	x	x	x	x	x	x	12	Children	Medicine
																	Specialist	Register 
																		Medical Report

15.	Conducting Parents	x	x	x	x	x	x	x	x	x	x	x	x	12	Programme 	Minutes Book
		Meeting															Coordinator,
																	Supervisor

16.	Preparing &	x	x	x	x	x	x	x	x	x	x	x	x	12	Programme	Statement of
Presenting Accounts															Coordinator	Accounts

17.	Documenting &						x						x		2	Programme	Documents Reporting															Coordinator, 
															Supervisor

#### BUDGETARY EXPLANATION (Annexure 2)

Item	Per Month	Rate	Amount	For 11 	
		Qty (Kg)	Rs.	Per mth.	months					Rs.

I. Provisions

1. Rice 	125	18	2250	24750

2. Dhal	8	52	416	4576

3. Oil	5	56	280	3080

4. Groceries	--	--	1500	16500

5. Vegetables	--	--	2000	22000

6. Kerosene	30 lit	30	900	9900

7. Egg	216 Nos.	1.5	324	3564

Sub-Total			7670	84370