Project Retrospection Report

Version No: 1.1

Date: 06-Jul-07

Project Name: Asha Delhi 20% Project

Delhi Chapter (Asha Delhi)

5, M-1 Street
IIT Delhi, Hauz Khas
New Delhi - 110 016,

India

Copyright Notice

This document contains project information of Asha for EducationTM & Asha Delhi. This document can be reproduced and the contents reused after information to Asha Delhi (ashadelhi@gmail.com). This document is for public information.

Revision History

| Version No | Date | Prepared by / Modified by | Significant Changes |
| --- | --- | --- | --- |
| 1.0 | 06-Jul -07 | Dhruva Kumar (dkitjb@gmail.com) | Created |
| 1.1 | 03-Sep-07 | Uday Gosain (uday_gosain@yahoo.com) | Updates |

Glossary

| Abbreviation | Description |
| --- | --- |

Table of Contents

1	Project Summary	3

1.1	Project Identification	3

1.2	Environment	3

2	Milestone Dates	4

3	Size, Effort and Schedule	4

4	Resources	5

4.1	Funds	5

4.2	Supervisors	6

5	Cost	6

6	Reviews	6

7	Defects	7

7.1	Root Cause Analysis	7

8	Risks	7

9	Skills Acquired	8

10	Reusable Components Generated	9

11	Other essential factors	9

# Project Summary

## Project Identification

| Project Sponsor Name | Asha for Education (Seattle/Munich Chapters) | Sponsor Contact details | Asha Delhi |
| --- | --- | --- | --- |
| Project Name | 20 % Reservation Project | Project Fields Team |  |
| Project Current Session Start Date | July -06 | End Date | June-07 |
| Actual effort (person weeks) |  | Group |  |

## Environment

|  | Description | Version Num |
| --- | --- | --- |
| Parivartan | The people from Parivartan are the front field executioners. |  |
| Asha Delhi | The funding, planning and monitoring group. |  |
| Public schools in Delhi | This clause is applicable to them. |  |
| Law used | Right to Information Act, 2005 |  |

# Milestone Dates

| Milestones | Planned completion date as per proposal. | Revised Completion Date | Actual Completion Date | Slippage in percentage (if any) | Remarks |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  | Va | Vb |  |
| Phase -1 | June-06 |  | June -06 |  |  | Surpassed the target |
| Phase -1 | June -07 |  | June -07 |  |  | Reached the target |

# Size, Effort and Schedule

| PLC Phase | SW Sub System | Size | Effort (in Person days / weeks / months) | Schedule |
| --- | --- | --- | --- | --- |
|  |  | Baselined | Actual | Baselined | Actual | Baselined | Actual |
|  |  |  |  |  |  | Start Date | End Date | Start Date | End date |
| Generating awareness |  |  |  |  |  | Jul -06 | 31-Aug-06 |  |  |
| Getting parents to sign on |  |  |  |  |  | Sept-06 | 31-Sep-06 |  |  |
| Collection of forms from school |  |  |  |  |  | Oct -06 | Feb -07 | Nov -06 | Feb -07 |
| Submission of forms |  |  |  |  |  | Jan–07 | March -07 | Jan –07 | Mar -07 |
| Final Admissions |  |  |  |  |  | Mar -07 | June -07 | Mar -07 | July -07 |
| Monitoring of admitted students |  |  |  |  |  | Continuous Process. |  | Continuous Process. |  |

# Resources

## Supervisors

| Session | Planned | Actual | Description | Remarks |
| --- | --- | --- | --- | --- |
| July -06 to June -07 | 6 | 4 | From Parivartan, | Good performance. |

# Cost

|  | Planned | Actual | Remarks |
| --- | --- | --- | --- |
| Funds | 18189.29 USD @ 42/ 14,691.35 EUR @ 53 | <Dhruva is calculating this> Seattle: Munich: EUR 2000 Asha Delhi NY A/c: |  |

# Reviews

Review of the project was done on monthly basis, by the coordinator of the project as well as by the Asha Delhi team.

# Defects

## Root Cause Analysis

| Issue | Root Cause |
| --- | --- |
| Non smooth flow of salaries. | Delays in getting vouchers signed Delays in getting statement of expenses from the supervisors Delays in courier Wrong vouchers sent Miscommunication Non availability of Asha Bangalore volunteers |
| Inappropriate monitoring system. | Non-Availability of time and lesser than expected number of project coordinators from AfE side. |
| Inadequate documentation of the project. | Time constraint |
| Lack of grass low level planning. | Lack of Professional Project Management approach |

# Risks

| Risks | Mitigation / Contingency strategy adopted. | Comments |
| --- | --- | --- |
| Change in the government policy. |  | The 20% has been reduced to 15% (5% for the power staff of the schools and 10% for open public under EWS) |
| Change in coordinators. | Handovers were done | However, the commitment levels were not achieved |
| Migration of field people to some other projects. | Single supervisor worked and achieved results |  |
| Fund allocation proposal failure. |  |  |
| Misuse of the clause. |  |  |

# Skills Acquired

| Member Name | Skill | Level |
| --- | --- | --- |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 |
| Ritu Mehra (Mob: +91 (0) 98993 58835) | Creating awareness, filing RTI Applications, follow up etc |  |  |  |  | 5 |  |
| Rekha Koli (+91 (0) 99103 49898) |  |  |  |  |  | 5 |  |
| Arif Hussain |  |  |  |  |  | 5 |  |
| Ram Asre |  |  |  |  |  | 5 |  |
| Abid Khan |  |  | 2 |  |  |  |  |

# Reusable Components Generated

| List of reusable components generated | Location of the reusable component |
| --- | --- |
| Project management experience. | Along with the project coordinator. |
| Workbook on how to go about the admission process | Asha Delhi Project Website |
| Some streamline processes | Along with the project coordinator. |
| Templates for budget and proposal | Asha Delhi project website |
| Retrospection Report Template | Asha Delhi project website |
| Project Plan Template | Asha Delhi project website |

# Other essential factors

Criteria for successful completion

| List of criteria for successful completion of project | 1 (Poor) | 2 (Satisfactory) | 3 (Good) | 4 (Very Good) | 5 (Excellent) |
| --- | --- | --- | --- | --- | --- |
| Number of children admitted |  |  |  |  |  |
| Enthusiasm of ALL project coordinators |  |  |  |  |  |
| Awareness in Parents |  |  |  |  |  |
| Project Coordination/Management |  |  |  |  |  |
| Salary and vouchers coordination |  |  |  |  |  |
| Monitoring of Admitted Students |  |  |  |  |  |

# Footnotes

1 - Not observed- Not observed for those skills where candidate claims proficiency but those that have not been assessed either at:

2 - Basic Understanding of the subject (Theoretical Knowledge) - Cannot be deployed in live project without close supervision. Has only theoretical knowledge and very little or no experience.

3 - Hands-on experience can deliver under limited supervision.

4 - Extensive experience - Can deliver independently.

5 - Subject matter expert (depth & breadth of the subject required) - Can coach & mentor others.

6 - Worked in Developing the Technology