Shikshamitra training program for Mukti teachers

Set up:

- Classes V, VII, IX on Mon, Wed, Fri while VI, VIII, X on Tue, Thu, Sat

- 3 teachers per center, ~10-30 children per center per class

- Usually 6:00-9:00am daily, 6:30-9:00am in winter

- English and math for 1 hr each, remaining for physical science

Basic infrastructure:

- No electricity

- 4 out of 8 centers benched, rest on floor

- Blackboard and chalk available

- Teachers will have to carry TLMs regularly

English

- Good reading but Bangla after each sentence, students can mostly follow with or without finger

- Spelling not great, vocab poor especially for words outside text

- Teaching is too oral especially for spellings, needs to be more writing based

- Teachers could play with words from the text

What is needed in English?

| Alphabets and alphabetical order | Pronunciation | Lower case, upper case |
| --- | --- | --- |
| Parts of speech (primary) | Word making | Tense (primary) |
| Spelling | English to Bengali | Vowel, consonant & article |
| Sentence making | Singular & Plural | Own name & others name |
| Punctuation (full stop & comma) | Gender | Opposite word |
| Has, have | Be verb | Vocabulary |

This amounts to the foundation course mentioned in our brochure and part of the second course (More English, Please! – http://www.shikshamitra-bengal.org/wp-content/uploads/2011/05/Shikshamitra_English.pdf).

Math

- Could read the problems and could respond to small multiplications and factoring

What is needed in math?

| Divisibility rule, primes, factorization | Mental math | Unitary methods |
| --- | --- | --- |
| Problem sum – reading and then translating to math | Decimal | Fraction |

Other needs

- Means to engage good and really good students –

[Suggested: have a stock of work /activities that can be attempted only if other work has been completed]

General observation

- Teachers’ unity good

- Teachers’ capacity good

Tentative plan:

Trainings hours: 9:00-4:00 daily with possibly a delayed start on day 1; each phase will span 5-6 days (see detailed plan below)

Given the volume of “what is needed” we strongly suggest that you close the centers on the training days. Otherwise there will not be enough time. Also if the teachers arrive after teaching and travelling they will be tired and won’t be able to take full advantage of the training offered.

English: Total of 9 days in 3 phases = 3 + 3 + 3

| Phase 1 | Phase 2 | Phase 3 |
| --- | --- | --- |
| Letters of alphabet Sounds of each letter Words with each letter Writing the alphabet – lower case and upper case Vowels and consonants Word making – phonetically Learning words (vocabulary) – by sight Sentence making – introduction | More vocab – opposites, gender etc. More about sentences More phonics and phonemes Parts of speech Singular and plural Writing small stories / small pieces for reading | Revision of sentences and punctuation Use of “be” verb Use of “has” and “have” Use of pronouns |

Math: Total of 5 days in 2 phases = 2 + 3

Phase 1 – primes, divisibility, factorization, mental math, problem sums and unitary method

Phase 2 – fractions and decimals

| Tentative dates | Plan |
| --- | --- |
| Jan 23-27 | Phase 1 – English = 3 days + math = 2 days |
| Mar end | Follow up = 2 days |
| Apr | Phase 2 – English = 3 days + math = 3 day |
| Jun end | Follow up = 2 days |
| Jul | Phase 3 – English = 3 days |
| Nov | Final evaluation = 2 days |

Both, English and math, with 2 follow ups in between and a final evaluation at the end

Follow ups and final evaluation

- will be combined for English and math

- each will span 2 days, 4 centers per day followed by discussion with the 12 teachers from those 4 centers

Travel plans

- Phases 1, 2 and 3 – we will reach Mukti on day 1 of the training and leave for Kolkata after the last day’s training i.e. 4-5 nights hotel stay per visit

- Follow ups and final evaluation – we will reach Raidighi the previous night and leave for Kolkata after the 2nd day’s discussion i.e. 2 nights hotel stay per visit

- There will be 2-3 of us, needing 2 rooms at the hotel –

  - Phase 1 and 2 = 3 people for 4+5 days in 2 trips

  - Phase 3, follow ups and final evaluation = 2 people for 2x4 days in 4 trips

Shikshamitra Training Budget

| Fees |  |  | 92000 |
| --- | --- | --- | --- |
| Training + final evaluation | Rs5000 x (9 + 5 + 2) days | 80000 |  |
| Follow ups | Rs3000 x (2 + 2) days | 12000 |  |
| Material cost |  |  | 10000 |
| Travel |  |  | 7566 |
| Train | Rs12 x 2 x (3 ppl x 2 trips + 2 ppl x 4 trips) | 336 |  |
| Auto (Mathurapur – Raidighi) | Rs45* x (3 ppl x 2 trips + 2 ppl x 4 trips) | 630 |  |
| Auto (Raidighi – Mukti) | Rs300 x (9 + 5) days | 4200 |  |
| Auto (Raidighi – Mukti centers) | Rs400 x (2 x 3) days | 2400 |  |
| Hotel |  |  | 13600 |
| Room | Rs300 x 2 rooms x (4 + 5 + 2 x 4) days | 10200 |  |
| Food | Rs200 x (4 + 5 + 2 x 4) days | 3400 |  |
| Total |  |  | 123166 |

* If autos don’t get full, they tend to delay. When time is limited, we might have to pay them 1 person’s extra fare to get them going. Auto fare (Mathurapur – Raidighi) is Rs15 per person.

- For travel and hotel we have tried to keep a slight overestimate of what actual costs might be.

- This is assuming one set of material per center. If Mukti wants, we can provide the material on a per teacher basis for additional cost.

- If there are changes to the plan in terms of different distribution of phases and trips, travel and hotel part of the budget will change accordingly.

In future:

Depending on how our work and relation progresses we can extend it to include training on middle school math based on WBBSE syllabus in 2013.

Additional Costs

COMBINED BUDGET