BALIA GRAM UNNAYAN SAMITY

Balia, Bahirkhand, Hooghly.

HALF-YEARLY PROGRAM REPORT ON PRE-PRIMARY EDUCATION PROGRAM FROM MAY 01, 2008 TO OCTOBER 31, 2008.

Name of the Project :- ASHA FOR EDUCATION.

Funded By :- ASHA KNOXVILLE.

During the above period 202 (M – 94, F – 108) Students from 3 to 6 age groups continuing Pre-Primary Education successfully and directly benefiting from the Program. Details list of the students are already sent to you in our earlier report vide our letter No. 16 / 1 /BGUS – 1087 dated – Oct. 17, 2008. We are enclosing a list of Teachers indicating the name, qualification and experience etc. for your kind information in Annexure – I.

We are also enclosing the comparative Educational & Nutritional status of the students in details in Annexure – II.

1.  The Objective of the Program :-

- To ensure Qualitative & Meaningful Pre-Primary Education for 202 Children.

- All round Development of the Students.

- To Prepare the Students for Qualitative Primary Education.

- To Prevent early drop-out.

2.  Program / Activities under the Project :-

- Selection of the Students.

- Capability building of the Teachers & Parents.

- Supplies Teaching Learning Materials as required.

- Recreational Facilities.

- Growth Monitoring, Health Check-up & Medicine.

- Supplies Nutritious Food.

- Mothers meeting & Teachers meeting.

- Regular Monitoring, Field visit, Performance grading of the Students’ through quarterly Test.

- Record keeping, Reporting & regular follow-up.

- Nutrition Education & Pre-Primary Education.

3.  Program implemented during the period (1/2 Yearly) :-

All the activities under above Sl. No. 2 are implemented during the above period & continuing.

- Selection, admission of the Students are already done.

- 4 Days Training Program for the Capability Building of Teachers are already done in 2 phases (Aug. 07 - 08, 2008 & Oct. 29 – 30, 2008) successfully Training provided by the Experienced Teachers & Resource Persons with active participation of the Pre-Primary Teachers.

- 45 Mothers meetings arranged in 9 Villages on different areas such as Education, Health, Nutrition, Superstition, Child-hood care & Development etc. etc. Average attendance of the Mothers are 90 % at the meeting.

- Teaching Learning Materials such as Books, Slate, Pencil, Ex-books, Black-board, Chalk, Duster, Charts relating to Alphabet, Birds, Fruits, Animals, Flowers, Yago-Asan etc. are provided along with different Play Materials, Dolls, Caram, Bagaduli, Bat-Balls etc. All the Students are highly delighted.

- Monthly Growth Monitoring is going on regularly. Half-yearly Health Check-up is already done by qualified Child specialist. Medicine also provided as required.

- Nutritious food are also provided to 202 Students for 130 Days. Mothers are helping the Teachers by cooking & distributing the Nutritious food among the Students.

- 8 Meetings of the Teachers are arranged during the period where all the Teachers submitted their Monthly reports & discussed about the Strengthens, Weakness, Problems, Performance, Progress at the meeting elaborately. Senior & Experienced Governing Board Members, Secretary, President, Supervisor are also present at the meeting & monitored the progress of the Program.

- 10 Trained & Experienced Teachers providing Pre-Primary Education to 202 students through Joyful Learning Method for Qualitative Development by active participation of the students.

4.  Achievements :- All the Students under the Program are day to day improving gradually. Their Educational  status, Nutritional Status etc. are developing as per enclosed Annexure – II.

5. 	Record Keeping :-

Attendance Register for Teachers & Students, Minutes Books, Stock Books, Growth Monitoring Register & Cards, Performance grading Register, Admission & Departure Register, follow-up Register for departed Students & Monthly Reports are maintaining & upgrading regularly. The above all records are verified by the Supervisors after each meeting on regular basis. Surprise visit to the Pre-Primary School is also done by the Supervisor, Seniors Members, Staff & G.B. Members.

6.  Finance :-

A.  We have received Rs. 93,979.60 /- (Rupees Ninety three thousand nine hundred seventy nine & Paise sixty) [$ 2,215 (Dollar Two thousand two hundred fifteen] only for the period from May 01, 2008 to Oct. 31, 2008 for Pre-Primary Education Program for 200 students of 3 – 6 age groups from ASHA Knoxville.

(a) Date of receipt the above fund :- June 14, 2008 .

(b) Date of crediting the Amount at our Account by our Banker :-  June 27, 2008.

(c) D/D No. & Date :- 159046, date – June 10, 2008.

B.    Head wise Budget & Expenditure during the above period :-

| Sl No. | Account Heads as per Contract Form | Sanctioned Amount as per Budget | Exp. during the above Period | Variance | Remarks |
| --- | --- | --- | --- | --- | --- |
| a. | Staff Salary – 10 Teachers | 36,000.00 | 36,000.00 | --- |  |
| b. | Supervisor Salary – 1 | 6,000.00 | 6.000.00 | --- |  |
| Sl No. | Account Heads as per Contract Form | Sanctioned Budget | Exp. During the above Period | Variance | Remarks |
| c. | Teaching Materials | 10,000.00 | 9,999.00 | 1.00 |  |
| d. | Nutrition | 24,000.00 | 24,097.50 | - 97.50 |  |
| e. | Health Check-up & Medicine | 6,000.00 | 4,251.00 | 1,749.00 |  |
| f. | Recreational Facilities | 2,500.00 | 2,500.00 | --- |  |
| g. | Capability Building | 1,000.00 | 976.00 | 24.00 |  |
| h. | Miscellaneous | 3,000.00 | 3,146.50 | - 146.50 |  |
|  | Total | 88,500.00 | 86,970.00 | 1,530.00 |  |

C.  Unutilized Balance if any :-  Cash in Hand  -   Nil.

(as on Oct. 31, 2008)           Cash at Bank – 7,009.60

7 . Conclusion :- Balia Gram Unnayan Samity is really grateful to all of them whose Contribution Support, Advice & Guidance are behind the humble success of the program. Expected that the above will be continuing in future to ensure the well-being of the Children as well as to reach its Goal. People are very interested about ASHA and it’s Programs. Thanks.