RESPONSE TO QUERIES

1. Side-by-side comparison of 2024, 2025, and 2026 budget proposals

Attached

2. Percentage of overall education budget supported by Asha

| Particulars | Amount (₹) | Percentage Share |
| --- | --- | --- |
| Overall Education Budget for 2025–26 | 2,19,81,903 | 100% |
| Asha for Education Contribution | 42,47,420 | 19.3% |

3. Audit reports for 2024 and 2025

Attached

4. Funds Utilization Reports (FUR) for last year

Attached

5. Other organizations supporting education (besides Asha)

The education program is supported by the following organizations:

- L and T Limited

- Mahindra World City

- Yatra Foundation

- Global Giving

- Dr. Mandawat

- Afshan & Berrie Foundation

- Peter Patel Scholarship

- Rajendra Jindal Scholarship

- STMicroelectronics Foundation

- Colgate

- Iron lady foundation

- Lord Deeds

6. 1800 overall for 3 years 2024-2027, last year ~1100 children how does that add up?

Children reached till 2025 is 1,629 (unique of 2024 and 2025). The remaining target will be met in 2026-27. Kindly refer the table below for details.

| Particulars | Unique children - 2024 |  | Repeated | Unique children - 2025 |  | Repeated - 2025 |  | Unique 2026 | Repeated 2026 | Total Unique (2024 to 26) | Repeated (2024-26) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Target | Achievement | Target | Target | Achievement | Target | Achievement | Target | Target |  |  |
| School-going children | 660 | 633 | 0 | 175 | 175 | 485 | 405 | 175 | 485 | 1,010 | 660 |
| SK children | 477 | 531 | 0 | 110 | 144 | 367 | 367 | 110 | 367 | 697 | 477 |
| RLC | 30 | 40 | 0 | 30 | 40 | 0 | 0 | 30 | 0 | 90 | 0 |
| School dropout children mainstreamed | 17 | 17 | 0 | 20 | 49 | 0 | 0 | 15 | 0 | 52 | 0 |
| Total | 1,184 | 1,221 | 0 | 335 | 408 | 852 | 772 | 330 | 852 | 1,849 | 1,137 |

7. Data of improvement in education from 2020 to 2025

a. SK children

In 2020, no learning level assessments were conducted due to COVID-19. The assessments resumed in December 2021. Assessment results show a positive shift, with more children progressing to Level 2 and Level 3, reflecting stronger foundational literacy and numeracy.

b. Government school children

Assessment findings from government schools indicate encouraging progress, with a greater number of children reaching Level 2 and Level 3, demonstrating improved foundational literacy and numeracy.

8. New activities introduced in 2026

For in-school children - WASH awareness sessions, Life skill sessions for children, SMC workshop

For out-of-school children – Exposure visits for SK alumni and Bal Manch members, and Retention study

9. Proposal aligned to ₹40 lakh cap from Asha

Proposal and Budget Attached

10. Updated out-of-school data for Kotra (comparison with 2017)

The data shows a significant reduction in out-of-school children aged 6 to 14 years in Kotda, from 47% in 2017 to 24% in 2025. The biggest improvement is in children who had never attended school, which declined from 34% to 13%, while dropout rates reduced slightly from 13% to 11%. This indicates stronger enrolment efforts, though retention still needs attention.

| Category | June 2017 (6 villages) | Dec 2025 (11 villages) |
| --- | --- | --- |
| Children out of school (includes never been and school dropout) | 47% | 24% |
| Never been school | 34% | 13% |
| School drop out | 13% | 11% |

- Target and achievements from previous period and the baseline numbers for current period

| Outcome | Baseline | Outcome Indicator (3 years) | Achievements 2024 | Achievement 2025 |
| --- | --- | --- | --- | --- |
| Increase in Regularity | 160 irregular children 473 children regular out of 633 enrolled (2024) | 70% increase from baseline | 98 made regular 21% increase in regularity | — |
|  | 206 irregular children 374 children regular out of 580 enrolled children (2025) | 70% increase from baseline | — | 165 made regular 44% increase in regularity |
| Reduction in school dropouts | 101 children identified as dropouts (baseline) | 80% reduction from baseline | 31 re-enrolled 31% reduction in school drop out | 49 re-enrolled (total of two years – 39+31 = 70) 70% reduction in school drop out |
| Children have appropriate learning levels - SK |  | 90% | 94% (Dec’24) | 95% (Dec’25) |
| Children have age-appropriate learning levels – Government School | 54% | 90% | 54% (Jun’24) | 69% (Dec’25) |
| Increased parental & community engagement in education | No active SMCs; irregular parent participation | Active participation of 5 SMCs & parent meetings | 1/5 SMC active 20% active SMCs Contribution of Rs. 2,48,340 received at SK | 5/5 SMCs active 100% active SMCs Contribution of Rs. 3, 31,020 received at SKs 33% increase in contribution |
| Primary-grade children attending SKs/RLCs become independent learners and they have improved age-appropriate learning levels | Limited learner independence | 75% | SK: 94%; RLC: 100% | SK: 95%; RLC: 100% |

12. Initiatives and outcomes from last year (2025)

Key highlights of 2025

- 1,071 children (41% girls) from 11 villages were supported through the program.

- 511 (192 girls) out-of-school children received quality education through 11 Siksha Kendras (SKs) and Residential Learning Camps (RLC).

- Work continued in 5 government schools, which benefited 580 children (255 girls, 325 boys) of primary grades.

- 246 (40 % girls) out of school children (167 SK children and 39 RLC children) were mainstreamed in 1st to 6th grades of government and private schools for continuing education, in July’25. Additionally, 5 girls, who are alumni of Siksha Kendras received scholarship support to pursue Science and Agriculture in 11thand 12 grade at Vidya Bhawan, a residential school in Udaipur.

- Out of 70 identified school dropout children (25 girls, 49 children), 17 girls were successfully re-enrolled in government schools. In addition, among 206 identified irregular children in Classes 1 to 5, of which 95 were girls, regular attendance was ensured for 165 children, including 74 girls. Similarly, in Classes 6 to 8, out of 48 irregular children (18 girls), 34 children, including 14 girls, were supported to become regular in school.

- The parents of children studying at SKs contributed Rs. 1,62,500 in the form of fees. The total community contribution for Shiksha Kendras (SKs) amounted to ₹70,110 towards rent, repair, and food items.