Tomorrow’s Foundation

CBEP-Community Based Education Program

Report – 1st July 09 to 15th August 09

Activities-

- The present status of CBEP CENTRE.

- We have enrolled the following students for the BC and Balwry centers.

The Table is given below---

BRIDGE COURSE

| Sl.No | Centre’s & Teacher’s Name | Age- 9 to 14 Years | Age above 14 years | Total | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | N.S.Sangha – Naren | M 11 F 2 | M 2 F 3 | 18 |  |
| 2 | Derojio Sikha | M 9 F 5 | M 3 F 11 | 28 |  |
| 3 | DeepSangha – Rekha | M 5 F 1 | M 4 F 1 | 11 |  |
| 4 | R.K.Club – Swati | M 0 F 9 | M 0 F 5 | 14 | For Girls |
| 5 | Bhandudal – Alpana | M 3 F 2 | M 2 F 5 | 12 |  |
| 6 | Sahapur I – Minati | M 6 F 3 | M 3 F 5 | 17 |  |
| 7 | N.C.Academy- Atiya | M 5 F 11 | M 0 F 6 | 22 |  |
| 8 | New Birds - Nazma | M 0 F 13 | M 0 F 9 | 22 | For Girls |
| 9 | T.E.B- Hayatun | M 4 F 12 | M 0 F 2 | 18 |  |
| 10 | Lotus - Naseema | M 12 F 15 | M 0 F 1 | 28 |  |
| 11 | Bhabikal – Susmita | M 0 F 0 | M 2 F 12 | 14 | Proposed as open school – out reach centre |
|  | TOTAL | M 55 F 73 Total 128 | M 16 F 60 Total 76 | 204 |  |

Balwadi

| Sl.No | Center’s & Teacher’s Name | Age- 5 to 9 Years | Age above 9 years | Total | Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Purbachal – Basanti | M 10 F 11 | M 0 F 0 | 22 |  |
| 2 | Sahapur II – Mira di | M 8 F 11 | M 0 F 0 | 19 |  |
| 3 | T.A- Anawari | M 13 F 12 | M 0 F 0 | 25 |  |
|  |  | M 31 F 34 Total 65 | M 0 F 0 | 65 |  |

- The Teachers’ Training process has been started in the project with the orientation of the teachers in the Bridge Course methods. The training programme was held on 08th (Kalighat) and 9th July(Tangra)

- Medical camp was held with Mothers of the community at New Shanti Sangha, Deep Sanha Mandir, and Tangra field office on 7th, 8th, 14th July.

- The BC books are provided to the teachers to the teachers after BC training on 29th/30th June.

- The process of group formation is going on the basis Existing Knowledge Testing  in each centre. The group formation is essential to impart age wise education  to various students of different educational status in each centre.

- Some children who are dropped out at higher classes ie. VIII to X have joined the project. The selection of the children for the Open school is on the process.   We have planned to put them in the Open School after the initial bridging in the centers.

- We are planning to start one open school out reach centre within CBEP in near future.

- Three more differently abled children have joined the centers. The total the no is now 15.

- Seasome Workshop India an organization (associated with CN  TV net work and Galli Galli Sim Sim) provide training to CBEP Balwadi teachers on 15th July. They have provide educational kits for each centers.  2 teachers from Balwry, Basanti & Anwari joined the training.

- Sahapur Milanthirtha (II) will act as a Balwry center and the Sahapur Milanthirtha (I) as a Bridge Course center.

- Requisitions are collected from the teachers of each centers .

- Workshop on Child Right and Child Protection Policy was conducted for all staff members of TF on 22nd July at TF Admin office, where all the teachers of CBEP have participated.

Other Related Works

- Official works, bill submission, salary, tiffin bill, rent distribution for the centers.

- Meeting were held in different centers

- Meeting with Open school teachers held at Kalighat Field Office.

.

Achievement-

- The process of mainstreaming has been completed. Total 493 are mainstreamed

- Till now 269 children are enrolled in 14 CBEP centers.

- Group formation process completed for the centers.

- BC training – II phase  and Balwadi Teachers Training II phase are completed

Problems-

.

- Few teachers are facing problems at class room situation to handle the adolescent children- to solve this problem we are planning to organize a training on adolescents behavior in August 09