**Project Work plan**

**1. The title**

Water, health and education for women and children of Thar

**2. Location**

6 villages of Osian block in the Thar Desert

**3. Duration**

One year (October 2012 to September 2013)

**4. Target population**

Women and children living in the project villages

**5. Project Plan**

GRAVIS and Asha for Education effort focusing on water security, healthcare and education have benefited the rural communities to a very good extent over the last 4 years. GRAVIS always learns from community and develops project for them and replicate best practices in area for sustainability. In coming year also GRAVIS would like to replicate outcomes of project intervention in Osian block. Schools will be continue with more focusing on girl child education, preventive healthcare will be part of project with special attention to health education to adolescence girls. Rainwater harvesting work will be done to reduce the drudgery of women and to promote the girl child education who are left out because of their involvement in procuring water for house.

**6. Activities**

**Women empowerment:**

Women organized in Self help groups will receive vocation training. More focus will be given to older SHGs of project villages.

**Water security:**

Rainwater harvesting Taanka will be constructed and taanka management training will be given to beneficiaries.

**Preventive healthcare:**

Medical camps will be organized to cater health needs of villagers specially women and children. Adolescence health camps will be organized for girls to educate them for personal health and hygiene and reproductive issue. This will help them to become healthier and responsive women in future.

**Primary Education:**

Asha for Education supported schools will be continued in Minno ki Dhnai and Dabri villages. Various events like *Gandhi* *Jyanti*, children day and Independence days will be celebrated in both of schools and children will be encouraged to take part in extracurricular activities.

**7. Proposed Budget**

|  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| **Oct 2012 to Sept 2013** | | | | | | |
|  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |
| Head |  |  |  | Unit | Unit Cost | Budget |
|  |  |  |  |  |  |  |
| Salary of Project Coordinator - Part time (1) | | | | 12 | 3500 | 42000 |
| Salary Field Worker (1) | |  |  | 12 | 5000 | 60000 |
| Travel |  |  |  | 12 | 3000 | 36000 |
| Vocational trainings of SHGs | | |  | 2 | 6000 | 12000 |
| Construction of taanka | |  |  | 7 | 18000 | 126000 |
| Taanka Management Training | | |  | 1 | 6000 | 6000 |
| ANC, Immunization and Medical camps | | | | 12 | 6000 | 72000 |
| Support to schools (2) | |  |  | 12 | 6000 | 72000 |
| Adolescence girls health camps | | |  | 2 | 6000 | 12000 |
| GRAVIS administration | |  |  | 12 | 2500 | 30000 |
|  |  |  |  |  |  |  |
| TOTAL |  |  |  |  |  | **468000** |